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The following information concerns progress at
day 40 of an Internet marketing project. Deter-
mine if the project is in control based on time
and cost to date. If not, what is the cost overage

or underage?
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Actual %
Activity Duration Budget _Cost _Completed

12 10 300 250 100
23 8 400 450 100
24 12 350 380 100
43 0 [ 0

35 18 405 400 70

56 16 450 - 0




