Requirements:

Font: Times New Roman

Size: Font size 12

Spacing: Single

12 APA Style reference and In-text citation

Minimum of 2700 words (Table of contents and References are not included in the 2700 words, but only the content of the written report)

++++++++++++++++++++++++++++++++++++++++++++++++++++++++++++++++++++++++++++++++++

CASE SCENARIO

You are the business owner of the ABC café in Hobart CBD in Tasmania, Australia with two other partners. Due to the extremely high rent, you are no longer able to afford to run the business, so you consult with an expert who will advise you on how to run the business successfully. The expert suggested that you move to a suburb (example: choose Glenorchy, Tasmania suburb) where the rent is affordable. You and your partners like the idea and decide to move to a new location, but before moving you must prepare a report with the help of your partners considering the points listed below.

++++++++++++++++++++++++++++++++++++++++++++++++++++++++++++++++++++++++++++++++++

TABLE OF CONTENTS FORMAT SHOULD BE FOLLOWED LIKE THE ONE BELOW

Table of Contents

EXECUTIVE SUMMARY	3

INTRODUCTION	3

REPORT ANALYSIS	3

PART A – PLANNING	3

(1) PARAMETERS / SCOPE OF THE PROJECT	3

Project name	3

Project period	3

Project objectives	3

Project stakeholders	3

Project budget	3

Resource requirements and allocation	3

(2) BREAKDOWN OF PROJECT OBJECTIVES	3

Deliverables	3

Work breakdown	4

Budget and allocation of resources	4

Timelines	4

Risk management	4

Recordkeeping and reporting	4

(3) WORK HEALTH AND SAFETY (WHS) RELATED RISK AND RISK MANAGEMENT MATRIX	4

(4) PROJECT BUDGET AND DISCUSSION WITH OTHER PARTNERS FOR APPROVAL	4

(5) PROJECT RELATED RESPONSIBILITIES OF PARTNERS AND CONSULTATION FOR NEXT STEP OF PLANNING	4

(6) LIMITATION RELATED TO REPORTING REQUIREMENTS	4

(7) PROJECT DOCUMENTATIONS	4

PART B – IMPLEMENTING AND MONITORING	4

PART C- 	5

CONCLUSION	5

REFERENCE LIST	5

ASSESSMENT 1: WRITTEN REPORT

First page only is for Table of Contents:

# TABLE OF CONTENTS

Put your table of contents here

Second page only is for Executive Summary:

# EXECUTIVE SUMMARY (130 words)

You need to explain in brief about the whole report in here.

# INTRODUCTION (170 words)

Explain in brief about the background of the organisation and why you executing this project. You need to make it bigger than executive summary

# REPORT ANALYSIS (1500 words)

Give overall review of the report which you are going to discuss in here.

## PART A – PLANNING

….. (1) PARAMETERS / SCOPE OF THE PROJECT - Briefly introduce your project by defining the parameters/scope of the project, including:

#### Project name: Relocation of the ABC cafe

Explain here

#### Project period: (How long it will take the project)

Explain here

#### Project objectives: (Why are we relocating; example: to be able to pay the rent, to decrease the cost, to increase efficiency, to increase quality)

Explain here

#### Project stakeholders: (Customers, local council, managers, etc.)

Explain here

#### Project budget: (how much it will take for the relocation; overall budget for this project)

Explain here

#### Resource requirements and allocation: (human resources, financial, furniture, materials, equipment’s, land or area or per. Think of the resources in the form of physical financial   and payment, and list them)

Explain here

….. (2) BREAKDOWN OF PROJECT OBJECTIVES -

- Break down your project objectives by creating milestones and drawing a Gantt chart or a table will be fine to represent the following:

Task 1: Planning (Under this task are Make schedule, prepare proposals, defining requirements, setting a budget, etc.)

Task 2: Locating a new property (Under this task are: Contacting the real estate agent, view of property, make a selection and signing a lease)

Task 3: Hiring staff (Under this task are employ training, work scheduling, set a budget)

Task 4: Design and infrastructure (Under this task are hire contractors, design lights and interiors, security setup)

Task 5: Purchasing restaurant equipment’s (Under this task are lease kitchen equipment’s, lease furniture, marketing equipment)

Task 6: Research more on your own

Task 7: Research more on your own

- Answer below must be in bullet points

#### Deliverables (This are why we are doing this project, and what could be our outcome)

Explain here (1 paragraph only)

#### Work breakdown (Make a reference from your Gantt chart. You should make a process diagram)

Make a reference from your Gantt chart and Make a process diagram

#### Budget and allocation of resources (Make a reference from your Gantt chart. List all the activities and how much budget you have set)

Explain here (1 paragraph only)

#### Timelines (Make a reference from your Gantt chart.)

Like for example: For week 1, you are doing planning, and just explain in words. All timeframes should be explained here.

#### Risk management (This is not linked with Gantt chart)

What is management risk?
Identify 5 related risks in bullet points for this business and it could be related to fire, machinery & equipment, compliance risks, slips, trips and fall, personal security, etc.

Under the bullet point for example below: How you can prevent the possible risk (Answer must be 3 ways to control that risk. Check the example below on how to answer this

Machinery and equipment risk

- How you can prevent the possible risk

- How you can prevent the possible risk

- How you can prevent the possible risk

#### Recordkeeping and reporting (1 paragraph) Explain.

What type of report that we need to keep for this business (examples: employee’s record, their supplies, record for this payroll, WHS incident.

### ….. (3) WORK HEALTH AND SAFETY (WHS) RELATED RISK AND RISK MANAGEMENT MATRIX

Example: How to answer this section

- : Identify (2) related risk that is related to your project of business and (1) WHS related risk

Example only below:

- Fire safety: Describe how will you manage this particular risk and who will be responsible for work. Answer must be in paragraph

- Machinery equipment: Describe how will you manage this particular risk and who will be responsible for work. Answer must be in paragraph

- Slips/trips/falls: Describe how will you manage this particular risk and who will be responsible for work. Answer must be in paragraph

- : Create a risk matrix and highlight those 3 risk in the risk management matrix

- : You need to select 1 WHS related risk and you need to write about team management of that risk.  How will you manage this particular risk and who will be responsible for work. Answer must be in paragraph 1-2 paragraph

### ….. (4) PROJECT BUDGET AND DISCUSSION WITH OTHER PARTNERS FOR APPROVAL

- You need to demonstrate your budget in form of a table.

Make table: In 1 column write a task, in another column 1 write about the budget, so for each task how much budget you have set, and at the end of the table, you can write the total budget.

- Discussion between the partners about this budget of the project for approval. Must be in a form of a summary notes.

### ….. (5) PROJECT RELATED RESPONSIBILITIES OF PARTNERS AND CONSULTATION FOR NEXT STEP OF PLANNING (200 words Dialogue script)

You can write you partners name, Anna, Dave, and Me (John). Write a dialogue script and discuss with your partners whether they are clear about their responsibilities and project requirements and consult with them regarding the next step in the planning process

There should be a discussion:

Anna might be doing planning and also looking for the location of the business

Dave might be responsible for hiring people

John is responsible for purchasing supplies.

In the dialogue discussion, just show that everybody is clear about their responsibilities and further planning action

Explain responsibilities and further planning action.

### ….. (6) LIMITATION RELATED TO REPORTING REQUIREMENTS

To answer this: Reporting requirements means who’s going to report their task to whom?

There are people who are doing HR job, there will be people looking after the finances, some people who look after purchases of supplies, etc.

Like for example, the Project manager is reporting to the owner; the HR is reporting to the Project Manager, etc.

Identify and explain the limitations of project regarding reporting requirements.

### ….. (7) PROJECT DOCUMENTATIONS

Complete the project documentations template below (fill them up) and get signed-off from your partners to conclude the project and gain approval

Project documentation Approval template

Background

| Project Name | Relocation of ABC cafe |
| --- | --- |
| Start Date | (The start date of the project) |
| End Date | (The end date of the project) |
| Budget | (Overall budget of the project) |
| Project manager | (John Doe) |
| Other management team involvement | (Could be owner, HR team, etc) |

| Stakeholder | Capacity assets and gaps | Desired future outcomes | Stakeholder influence/impact |
| --- | --- | --- | --- |
| Note: Direct and indirect stakeholders should be listed here | What are the stakeholder’s resources and strengths that can help address the problem that the project strives to solve? What are the stakeholder’s needs and vulnerabilities that the project attempts to bridge? | What are the desired outcomes for the stakeholder as a result of project implementation? | How strong is the stakeholder’s influence to impact the direction and outcome of the project? i.e. High/Medium/Low |

Stakeholder analysis and capacity assessment

Project outcome (Outcome to your objective of the project)

| Outcome one | (State a positive outcome) |
| --- | --- |
| Outcome two | (State a positive outcome) |
| Outcome three | (State a negative outcome) |

Management comments

| Name/position | Jayson/Project Manager |
| --- | --- |
| Review date | (On what day he reviewed this report) |
| Comments | (About the project plan, about whether the project is viable, or about the staff, or budget, etc.) (Just think of anything) |
| Signature |  |

## PART B – IMPLEMENTING AND MONITORING

You and your partners have found a new location to open your café but before opening the business you need approval from the council. Once you’ve gained approval to open the café, the next step is to implement and monitor the plan. You and your partners must implement the project plan you finalised in Part A by considering the following points below:

1. Identify three (3) types of data for record keeping. How would you ensure financial record keeping is complete and accurate? (200 words)

2. Develop three (3) strategies you could use to implement and monitor the plan for managing project finances, resources and quality. (200 words)

3. Review with your partners the project outcomes with your project scope and the plan you prepared in part A. (100 words)

4. Check your risk management matrix prepared in Part A and ensure your project outcomes are met and deliverables are achieved. (100 words)

## PART C- (200 words)

Description You are to pretend that your classmate are your business partners and team members. During the role play you must ensure you encourage your team members to give you feedback and cover the following points:

Consult with your team members about planning the project, taking their views into account. Delegate the authority to manage the project.

- Discuss with your team the new role and responsibilities allocated to the staff at the new location and provide support in the transition period. (This one is not for the current project. This right after the project, or after this project is ended and we are starting a business again. If the current staff members responsibilities will be changed then how will you support them during the transition)

- Discuss the overall lessons learned from the project.

## CONCLUSION (100 words)

Explain conclusion here.

# REFERENCE LIST

Give minimum 12 references