Space Systems Technical Corporation

Ansari X Prize Gauchito Rocket

Mohave, California

Table of Contents

Executive Summary ........................................................................  page 3

Key Stakeholders ............................................................................  page 3

Business Needs    ............................................................................. page 3

Proposal 7/8 Scale Ansari X Gauchito Rocket …………………… page 4

1.0 Scope Management Plan ..........................................................  page 5–11

Project Scope Change Order...........................................................  page 8

2.0 Schedule Management Plan.....................................................   page 12–39

Appendix MM: Milestones...........................................................    page 16

Appendix CR: Change Request Form……………………………   page 17–18

Appendix WT: WBS at Tracked Level…………………………..   page 19–21

Appendix WG: WBS Milestone Gantt …………………………..   page 22–25

Appendix WR: WBS with Resources Leveled…………………...   page 26–38

Appendix ND: Gauchito Network Diagram………………………  page 39

3.0 Cost Management Plan.............................................................  page 40–50

Example Cost Management Report................................................  page 47

4.0 Quality Management Plan......................................................     page 51–75

Project Quality Control................................................................     page 55–70

Project Audits & Quality Reviews …………………………….      page 74–75

5.0 Staffing Management Plan …………………………………     page 76–82

6.0 Communications Management Plan ………………………..     page 83–87

Enclosure I ……………………………………………………....    page 85

Project Communications Planner ………………………………     page 86–87

7.0 Risk Management Plan …………………………………….    page 88–93

Risk Register ……………………………………………………   page 92

8.0 Procurement Management Plan …………………………….   page 94–98

Probability and Impact Matrix …………………………………    page 97

Benchmark ……………………………………………………...   page 98

Appendix A Project Charter ……………………………………   page 99–104

Appendix B Product Description ………………………………   page 105–106

Appendix C Preliminary Scope Statement …………………….    page 107–112

Appendix D Work Breakdown Structure ………………………   page 113–118

Appendix E  Cost Rollup Estimates……………………………    page 119–120

Appendix F Scheduled Start Dates…………………………….    page 121–122

Appendix G Responsibility Assignment Matrix ……………...     page 123–124

Appendix H Performance Measurement Baselines …………..     page 125

Appendix I Major Milestones ………………………………...     page 126

Appendix J Key or Required Staff ……………………………     page 127

Appendix K Key Risks ……………………………………….     page 128

Appendix L Constraints ………………………………………     page 129

Appendix M Assumptions ……………………………………     page 130

Appendix N Construction Plans ………………………………    page 131–135

Works Cited …………………………………………………..     page 136

Executive Summary

Space Systems Technology Corporation (SST)   is a worldwide leader in providing business solutions. Space Systems Business Technology Corporation will engineer and build a 7/8 scale model of the Ansari X Gauchito Rocket. The project’s start date is May 22, 20XX, and the end date is July 26, 20XX. The order of magnitude estimate for the project budget will be $63,000.

The requirements in this project, the project scope, project proposal, budget utilization, cost, constraints, requirements, project plan, responsibilities, and the risk factors have all been discussed and worked on.

Space Systems Technology Corporation, the engineering firm, has contracted for the following reasons:

- The personnel are highly skilled and experienced in the field.

- Over 30 years experience in successful engineering.

In conclusion, Space Systems Technology Corporation is a firm specializing in the production of built to scale, fully functioning models.

Key Stakeholders

Pablo de Leon & Associates along with the members of Space Systems Technology Corporation are the key stakeholders for the Ansari X Gauchito Rocket project.

Business Needs

Pablo de Leon & Associates requires Space Systems Technology Corporation to build a functioning scaled rocket based on its design for entry into the Ansari X Prize Cup. This scaled rocket prototype will allow Pablo de Leon to test their design for reduced cost and prove the feasibility of building a full-sized rocket.

Proposal 7/8 Scale Ansari X Gauchito Rocket

1.0 Scope Management Plan

1.1 Scope Definition

The project scope for the Gauchito rocket will be defined by the project charter and preliminary scope statement as well as the scope management plan and all approved change requests. The work breakdown structure presents the project deliverables in a hierarchical manner, and the definition will include the completed work breakdown structure down to the work package level. The work breakdown structure will be based upon the construction plan, which will be strictly adhered to. In order to ensure proper definition of scope, the project manager will meet with all of the key personnel regarding every facet of this project. All phases of the project will be broken down according to amount of effort required into smaller work packages.

1.2 Scope Documentation

The project scope will be documented through an engineering specs descriptive document that is provided by the customer and has been inputted into the project charter. If there are any discrepancies between the product description and the product requirements, as the product description states the rocket must be 37 feet long, the project charter requires a 7/8 scale, which is a 43 foot long rocket; then the project manager and the team will discuss this with the customer and define the actual length. There will be an internal central database set up for this project specifically to allow all project team members access to the same information regarding the exact scope for this project. All documentation specific to this project shall be archived and tracked within this database.

1.3 Scope Verification

The project scope shall be verified through the project scope statement, the project scope management plan, and constant communication with the project sponsor to ensure the deliverables are being met and understood. An inspection of each deliverable shall be performed and shall be compared to the construction plan and the work breakdown structure. The scope deliverables are understood to be as follows:

1.0 ASSEMBLE ENGINE MOUNT

2.0 FIN PREPARATION

3.0 MARK FIN AND LAUNCH LUG LINES

4.0 INSERTING ENGINE MOUNT

5.0 ATTACH FINS

6.0 ATTACH SHOCK CORD

7.0 ASSEMBLE NOSE CONE

8.0 ATTACH PARACHUTE/SHOCK CORD

9.0 ATTACH LAUNCH LUG

10.0 PAINTING THE ROCKET

11.0 APPLICATION OF DECALS

12.0 APPLYING CLEAR COAT

13.0 DISPLAY NOZZLE ASSEMBLY

14.0 ROCKET PREFLIGHT

15.0 PREPARE FOR TEST LAUNCH

1.4 Scope Management

The project scope will be managed through the utilization of change requests to the project and shall be reviewed by the subject matter expert it affects, the project manager, and the sponsor. Identification of any risk to the project regarding the change as well as the effect on the schedule of the project and cost will be considered. No changes will be approved until the project manager and team meet with the sponsor to validate the scope. The project manager and customer need to meet to get the customer’s feedback on any requested changes after they have been validated through the scope to ensure that all of the deliverables are still being met if the change is approved. The project manager and the sponsor must both sign off and approve any changes requested. Any and all corrective actions that are suggested will be considered in the same manner as the requested changes. Corrective actions that need to be taken will be signed off on by the project manager and the sponsor and will be implemented by the project manager. The following change order form will be utilized during the duration of this project.

Project Scope Change Order

Project Name: Ansari X Prize Cup-Gauchito Rocket

Project Manager: Julie Davis

Project Tracking Number: PMGT 605-001           Date:

Summary of Change:

Rationale for Change:

Brief overview of the impact of this change on . . .

- Project schedule:

- Quality of deliverables:

- Costs:

- Stakeholders and/or core team members:

- Other deliverables, including amount and quality:

Change approved by (signatures):

Sponsor Jeff Tyler: ___________________________________________ Date: ___________

Project Manager Julie Davis: ____________________________________ Date: _________

The project scope will also be managed through the project scope statement, the work breakdown structure, the project scope management plan, and performance reports, as well as any approved change requests and all work performance information. The implemented change control procedures will be followed with no exceptions. Variance analysis shall be utilized when needed.

1.5 Scope Control

The project scope will be controlled by utilizing the project scope statement, work breakdown structure, work breakdown structure dictionary, project scope management plan, all project performance reports, all approved change requests, and work performance information, which are the scope inputs of the project. The tools used will be the change management plan, variance analysis, and any replanning needed to stay within the scope of the project and on task to complete the deliverables, as well as the utilization of the configuration management system. The outputs for the scope control will include any project scope updates, all work breakdown structure updates, all scope baseline updates, any requested changes, any recommended corrective actions, any organizational process asset updates, and any updates to the project management plan. All changes, including a preliminary high-level evaluation of schedule, cost, labor, etc., will be presented to the Configuration Control Board (CCB) immediately as time is of the essence in the short-term project to determine if any changes should be approved.

1.5.1 Causation of Scope Changes

Please note the most frequent causes of scope change requests include:

- Errors in Omissions—Change in requirements that would result in schedule delays and cost increases that are not allowed in this project at all, due to the short time frame and the race to win the Ansari X Prize.

- Value-Adding Opportunities—The unforeseen advent of new technology that could add value to the project. Maintain the scope of the project if the new opportunity does not have sufficient return on investment value to offset any risk that could be involved utilizing the new product. We are contracted to utilize only those tool sets that were previously agreed upon. No changes will be acceptable unless signed off on by the CCB, the PM, and the sponsor.

- Competitive Pressures—Other competitors getting closer to being the first to develop the winning rocket may cause our team to have to speed up the schedule and work holidays and weekends.

- Schedule Slippage—Can sometimes force the team to reduce the scope of the project. This is not an option with this project as it is so detailed and short term. Do not forget this team wants to be first to have a fully functioning rocket to enable Pablo de Leon & Associates to win the Ansari X Prize Cup.

1.6 Scope Development & Breakdown

Process for developing the WBS from the detailed scope statement will be completed through the use of subject matter experts (SMEs). A project team review will be conducted after the project manager breaks down each deliverable into the level of the work package, where it can be assigned to one person, and a cost control account created for that work package, which must be less than 80 hours. For example, cutting and sanding the fins is decomposed into cutting fins as one task and sanding fins as one task. The tasks may then each be further decomposed into cutting fin #1 and sanding fin #1, with a work package for each fin for cutting and one for sanding.

1.7 Formal Scope Verification

Formal verification of the deliverable will be done through the utilization of the WBS, the project charter, and the scope management plan, as well as any signed, approved change requests and updates. This will be done through reviewing the deliverables and their requirements at each milestone by the PM and sponsor.

  - Formal Acceptance

Formal acceptance of deliverable will be obtained through the above-stated verification

process so that when the rocket is complete, the customer can review all of the formal verification requirements and test procedures that the sponsor previously signed off on with the PM. Formal acceptance is considered complete when the customer comes to pick up the rocket no later than 3 days after completion of contract deliverables.

# 2.0 Schedule Management Plan

### Objectives

# The purpose of this document is to define and document how changes to the schedule will be managed for this project.

### Overview

The project shall be managed by means of an established work breakdown structure (WBS). This WBS shall be the basis for establishing project schedule and for definition of project tasks and deliverables. The project manager (PM) shall collect actual completion and resource utilization data from the team members in order to calculate actual performance against predicted cost and schedule. This data shall be presented to the program manager in the form of a weekly project status report.

Task status and resource utilization statistics shall be reported to the PM utilizing the elements of the WBS. The project shall be controlled using Microsoft Project to establish project tasks, dependencies, and schedule. WBS activity decomposition shall be such that tasks can be completed in a maximum one-week time frame. Credit for task progress shall only be awarded upon task completion. Team members shall provide weekly statistics on resource expenditures by task as well as information concerning task completion. This information shall then be compiled to provide schedule status to the sponsor.

2.1 Assumptions

- The materials and equipment will arrive one week prior to project start date.

- All necessary personnel will be available at the time of the project start.

- The contracts will be followed as written without any delays or difficulties.

### 2.2 Schedule Variance Response Process

# Once the project schedule is base-lined, the PM is responsible for ensuring that actual effort and start and end dates are entered for each activity. This data is essential to establish whether schedule variances exist. When variance is required, the PM is the primary decision maker; for major problems, the sponsor will be the ultimate decision maker.

# 2.3 Major Problems

    - On a regular basis, but not less than once per week, the PM will create an earned value report. Using this report, the PM will identify and isolate both positive and negative schedule variances.

    - When a variance exceeds +/– 5%, the PM must determine what is causing the variance and decide if the variance requires corrective action.

    - If corrective action is required, it is up to the discretion of the sponsor as to whether a schedule change request is necessary or if the variance can be absorbed within the existing project schedule. If a schedule change request is necessary, it is submitted through the standard schedule change control procedures as outlined in the following.

    - Notification will be sent to the sponsor and all functional managers via email; when required, a copy of the signed change request form will be attached.

2.4 Minor Problems

    - Minor variances will be absorbed into the project through schedule changes or shifting of project resources.

### 2.5 Schedule Change Control Processes

  - All schedule modifications must go though the following change control process:

    - Identify and assess the schedule change.

    - Fill out and submit a “Change Request Form,” along with required supporting documentation to the PM.

    - The PM will review the change request and may possibly request additional documentation prior to review by the CCB.

    - The CCB will evaluate the change. Using the “Change Request Form,” the CCB will mark the change as:

      - Approved, in which case the PM will incorporate the change and adjust other project planning factors as necessary.

      - Approved pending additional supporting documentation, in which case the PM will specify and coordinate gathering of the required documentation, incorporate the change, and adjust other project planning factors as necessary.

      - Denied, in which case the PM will notify the requestor of the status and reason for denial.

    - The PM will document the change request outcome and as necessary update WBS and schedule documentation if impacted.

### 2.6 Schedule References

A WBS for the level the project will be tracked is in Appendix WT.

A resource-leveled project plan is available in Appendix WR.

A time-based network diagram is available in Appendix ND.

A milestone chart is available in Appendix MM.

A change request form is in Appendix CR

# Appendix MM: Milestones

| Name | Finish Date |
| --- | --- |
| 1.0 ASSEMBLE ENGINE MOUNT | 6/5/20XX |
| 2.0 FIN PREPARATION | 5/25/20XX20XX |
| 3.0 MARK FIN AND LAUNCH LUG LINES | 5/30/20XX20XX |
| 4.0 INSERTING ENGINE MOUNT | 6/9/20XX20XX |
| 5.0 ATTACH FINS | 6/16/20XX20XX |
| 6.0 ATTACH SHOCK CORD | 5/26/20XX20XX |
| 7.0 ASSEMBLE NOSE CONE | 5/23/20XX20XX |
| 8.0 ATTACH PARACHUTE/SHOCK CORD | 6/2/20XX20XX |
| 9.0 ATTACH LAUNCH LUG | 6/22/20XX20XX |
| 10.0 PAINTING THE ROCKET | 6/29/20XX20XX |
| 11.0 APPLICATION OF DECALS | 7/6/20XX20XX |
| 12.0 APPLYING CLEAR COAT | 7/7/20XX20XX |
| 13.0 DISPLAY NOZZLE ASSEMBLY | 7/13/20XX20XX |
| 14.0 ROCKET PREFLIGHT | 7/20/20XX20XX |
| 15.0 PREPARE FOR TEST LAUNCH | 7/26/20XX20XX |

# Appendix CR: Change Request Form

Project Name:

Date Request Submitted:

Title of Change Request:

Change Order Number:

Submitted by: (name and contact information)

# Change Category:

Scope    Schedule    Cost   Technology   Other

Description of change requested:

Events that made this change necessary or desirable:

Justification for the change/why it is needed/desired to continue/complete the project:

Impact of the proposed change on:

Scope:

Schedule:

Cost:

Staffing:

Risk:

Other:

Suggested implementation if the change request is approved:

Required approvals:

| Name/Title | Date | Approve/Reject |
| --- | --- | --- |

Reference:

Schwable, K.(2015). Information technology project management, 8th ed. Cengage Learning. Retrieved from https://www.cengagebrain.com/shop/ProductDisplay?urlRequestType=Base&catalogId=10057&categoryId=&productId=666770&errorViewName=ProductDisplayErrorView&urlLangId=-1&langId=-1&top_category=&parent_category_rn=&storeId=10151

# Appendix WT: WBS at Tracked Level

| Name | Duration |  | Start Date | Finish Date |
| --- | --- | --- | --- | --- |
| 1.0 ASSEMBLE ENGINE MOUNT | 95 |  | 5/22/20XX | 6/5/20XX |
| -1.1 Measure, Mark, and Cut Engine Tube | 35 |  | 5/22/20XX | 5/26/20XX |
| -1.2 Cut Engine Tube | 2 |  | 5/26/20XX | 5/26/20XX |
| -1.3 Glue, Tube, Assemble Hook | 7 |  | 5/26/20XX | 5/30/20XX |
| -1.4 Assemble Mylar Ring to Tube | 9 |  | 5/30/20XX | 5/30/20XX |
| -1.5 Assemble Yellow Engine Block to Engine Mount Tube |  | 10 | 5/31/20XX | 5/31/20XX |
| -1.6 Assemble Centering Rings |  | 22 | 6/1/20XX | 6/2/20XX |
| -1.7 Application of Glue Fillets |  | 10 | 6/5/20XX | 6/5/20XX |
| 2.0 FIN PREPARATION |  | 30 | 5/22/20XX | 5/25/20XX |
| -2.1 Sand/Cut Fins |  | 8 | 5/22/20XX | 5/22/20XX |
| -2.2 Cutting Out Fins |  | 12 | 5/23/20XX | 5/24/20XX |
| -2.3 Stack and Sand Fins |  | 10 | 5/24/20XX | 5/25/20XX |
| 3.0 MARK FIN AND LAUNCH LUG LINES |  | 33 | 5/22/20XX | 5/30/20XX |
| -3.1 Cut - Tape |  | 13 | 5/22/20XX | 5/25/20XX |
| -3.2 Remove guide, connect fins and lug lines, extend LL line |  | 16 | 5/25/20XX | 5/30/20XX |
| -3.3 Extend Launch Lug Line |  | 4 | 5/30/20XX | 5/30/20XX |
| 4.0 INSERTING ENGINE MOUNT |  | 43 | 6/6/20XX | 6/9/20XX |
| -4.1 Mark Inside of Tube @ 5/8" Where LL is |  | 7 | 6/6/20XX | 6/6/20XX |
| -4.2 Glue Tube |  | 5 | 6/6/20XX | 6/7/20XX |
| -4.3 Assemble Engine Hook |  | 18 | 6/7/20XX | 6/8/20XX |
| -4.4 Gluing Center Body Ring |  | 13 | 6/9/20XX | 6/9/20XX |
| 5.0 ATTACH FINS |  | 73 | 6/12/20XX | 6/16/20XX |
| -5.1 Attach Fin #1 |  | 10 | 6/12/20XX | 6/13/20XX |
| -5.2 Attach Fin #2 |  | 10 | 6/12/20XX | 6/13/20XX |
| -5.3 Attach Fin #3 |  | 10 | 6/12/20XX | 6/13/20XX |
| -5.4 Attach Fin #4 |  | 10 | 6/12/20XX | 6/13/20XX |
| -5.5 Check Fin Alignment |  | 16 | 6/13/20XX | 6/15/20XX |
| -5.6 Allow Glue to Dry |  | 17 | 6/15/20XX | 6/16/20XX |
| 6.0 ATTACH SHOCK CORD |  | 44 | 5/22/20XX | 5/26/20XX |
| -6.1 Cut Out Shock Cord Mount |  | 5 | 5/22/20XX | 5/22/20XX |
| -6.2 First Glue Application |  | 12 | 5/22/20XX | 5/24/20XX |
| -6.3 Second Glue Application |  | 8 | 5/24/20XX | 5/25/20XX |
| -6.4 Squeeze and Hold |  | 6 | 5/25/20XX | 5/25/20XX |
| -6.5 Attaching Shock Cord Mount |  | 13 | 5/25/20XX | 5/26/20XX |
| 7.0 ASSEMBLE NOSE CONE |  | 16 | 5/22/20XX | 5/23/20XX |
| -7.1 Glue Nose Cone |  | 16 | 5/22/20XX | 5/23/20XX |
| 8.0 ATTACH PARACHUTE/SHOCK CORD |  | 18 | 5/30/20XX | 6/2/20XX |
| -8.1 Attach Lines |  | 7 | 5/30/20XX | 5/31/20XX |
| -8.2 Attach Parachute |  | 5 | 5/31/20XX | 6/1/20XX |
| -8.3 Tie Lines |  | 6 | 6/1/20XX | 6/2/20XX |
| 9.0 ATTACH LAUNCH LUG |  | 32 | 6/19/20XX | 6/22/20XX |
| -9.1 Glue Launch Lines |  | 4 | 6/19/20XX | 6/19/20XX |
| -9.2 Application of Glue Fillets |  | 28 | 6/19/20XX | 6/22/20XX |
| 10.0 PAINTING THE ROCKET |  | 64 | 6/22/20XX | 6/29/20XX |
| -10.1 Apply First Coat |  | 16 | 6/22/20XX | 6/23/20XX |
| -10.2 Sand |  | 8 | 6/23/20XX | 6/23/20XX |
| -10.3 Apply Final Coat |  | 40 | 6/26/20XX | 6/29/20XX |
| 11.0 APPLICATION OF DECALS |  | 35 | 6/29/20XX | 7/6/20XX |
| -11.1 Apply First Decal |  | 5 | 6/29/20XX | 6/29/20XX |
| -11.2 Apply Second Decal |  | 5 | 6/29/20XX | 6/30/20XX |
| -11.3 Apply Third Decal |  | 5 | 6/30/20XX | 6/30/20XX |
| -11.4 Apply Fourth Decal |  | 5 | 6/30/20XX | 7/3/20XX |
| -11.5 Apply Fifth Decal |  | 5 | 7/3/20XX | 7/5/20XX |
| -11.6 Apply Sixth Decal |  | 5 | 7/5/20XX | 7/5/20XX |
| -11.7 Apply Seventh Decal |  | 5 | 7/5/20XX | 7/6/20XX |
| 12.0 APPLYING CLEAR COAT |  | 16 | 7/6/20XX | 7/7/20XX |
| -12.1 Apply Clear Coat to Entire Rocket |  | 16 | 7/6/20XX | 7/7/20XX |
| 13.0 DISPLAY NOZZLE ASSEMBLY |  | 32 | 7/10/20XX | 7/13/20XX |
| -13.1 Spray Nozzle Base White |  | 18 | 7/10/20XX | 7/11/20XX |
| -13.2 Apply Glue |  | 14 | 7/12/20XX | 7/13/20XX |
| 14.0 ROCKET PREFLIGHT |  | 42 | 7/13/20XX | 7/20/20XX |
| 14.1 Prepare |  | 13 | 7/13/20XX | 7/17/20XX |
| 14.2 Spike |  | 4 | 7/17/20XX | 7/17/20XX |
| 14.3 Fold |  | 4 | 7/17/20XX | 7/18/20XX |
| 14.4 Roll |  | 4 | 7/18/20XX | 7/18/20XX |
| 14.5 Re-insert |  | 17 | 7/18/0XX | 7/20/20XX |
| 15.0 PREPARE FOR TEST LAUNCH |  | 32 | 7/21/20XX | 7/26/20XX |
| -15.1 Insert Engine |  | 32 | 7/21/20XX | 7/26/20XX |

# Appendix WG: WBS Milestone Gantt

| Name | Duration (hours) | 8 | 16 | 24 | 32 | 40 | 48 | 56 | 64 | 72 | 80 | 88 | 96 | 104 | 112 | 120 | 128 | 136 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1.0 ASSEMBLE ENGINE MOUNT | 65 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.0 FIN PREPARATION | 19 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.0 MARK FIN AND LAUNCH LUG LINES | 17 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.0 INSERTING ENGINE MOUNT | 28 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5.0 ATTACH FINS | 42 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 6.0 ATTACH SHOCK CORD | 18 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 7.0 ASSEMBLE NOSE CONE | 10 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 8.0 ATTACH PARACHUTE/SHOCK CORD | 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 9.0 ATTACH LAUNCH LUG | 12 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 10.0 PAINTING THE ROCKET | 33 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 11.0 APPLICATION OF DECALS | 28 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 12.0 APPLYING CLEAR COAT | 10 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 13.0 DISPLAY NOZZLE ASSEMBLY | 20 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 14.0 ROCKET PREFLIGHT | 11 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 15.0 PREPARE FOR TEST LAUNCH | 5 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

| Name | Duration (hours) | 144 | 152 | 160 | 168 | 176 | 184 | 192 | 200 | 208 | 216 | 224 | 232 | 240 | 248 | 256 | 264 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1.0 ASSEMBLE ENGINE MOUNT | 65 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.0 FIN PREPARATION | 19 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.0 MARK FIN AND LAUNCH LUG LINES | 17 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.0 INSERTING ENGINE MOUNT | 28 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5.0 ATTACH FINS | 42 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 6.0 ATTACH SHOCK CORD | 18 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 7.0 ASSEMBLE NOSE CONE | 10 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 8.0 ATTACH PARACHUTE/SHOCK CORD | 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 9.0 ATTACH LAUNCH LUG | 12 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 10.0 PAINTING THE ROCKET | 33 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 11.0 APPLICATION OF DECALS | 28 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 12.0 APPLYING CLEAR COAT | 10 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 13.0 DISPLAY NOZZLE ASSEMBLY | 20 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 14.0 ROCKET PREFLIGHT | 11 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 15.0 PREPARE FOR TEST LAUNCH | 5 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

| Name | Duration (hours) | 272 | 280 | 288 | 296 | 304 | 312 | 320 | 328 | 336 | 344 | 352 | 360 | 368 | 376 | 384 | 392 | 400 | 408 | 416 | 424 | 432 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1.0 ASSEMBLE ENGINE MOUNT | 65 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.0 FIN PREPARATION | 19 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.0 MARK FIN AND LAUNCH LUG LINES | 17 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.0 INSERTING ENGINE MOUNT | 28 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5.0 ATTACH FINS | 42 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 6.0 ATTACH SHOCK CORD | 18 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 7.0 ASSEMBLE NOSE CONE | 10 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 8.0 ATTACH PARACHUTE/SHOCK CORD | 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 9.0 ATTACH LAUNCH LUG | 12 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 10.0 PAINTING THE ROCKET | 33 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 11.0 APPLICATION OF DECALS | 28 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 12.0 APPLYING CLEAR COAT | 10 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 13.0 DISPLAY NOZZLE ASSEMBLY | 20 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 14.0 ROCKET PREFLIGHT | 11 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 15.0 PREPARE FOR TEST LAUNCH | 5 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

# Appendix WR: WBS with Resources Leveled

| Name | Duration | Start Date | Finish Date | Resource Names |
| --- | --- | --- | --- | --- |
| 1.0 ASSEMBLE ENGINE MOUNT | 95 | 5/22/20XX20XX | 6/5/20XX20XX |  |
| 1.1 Measure, Mark, and Cut Engine Tube | 35 | 5/22/20XX20XX | 5/26/20XX20XX |  |
| -1.1.1 Lay ruler along engine tube | 5 | 5/22/20XX20XX | 5/22/20XX20XX | Fitter #1 |
| -1.1.2 Measure engine from left of engine tube @ 1/8" | 5 | 5/22/20XX | 5/23/20XX | Draftsman #1 |
| -1.1.3 Mark left end of engine tube @ 1/8" | 5 | 5/23/20XX | 5/23/20XX | Draftsman #1 |
| -1.1.4 Measure engine from left of engine tube @ 3/4" | 5 | 5/23/20XX | 5/24/20XX | Draftsman #1 |
| -1.1.5 Mark from left of engine tube @ 3/4" | 5 | 5/24/20XX | 5/25/20XX | Draftsman #1 |
| -1.1.6 Measure engine tube from left of engine tube @ 1 1/2" | 5 | 5/25/20XX | 5/25/20XX | Draftsman #1 |
| -1.1.7 Mark from left of engine tube @ 1 1/2" | 5 | 5/25/20XX | 5/26/20XX | Draftsman #1 |
| -1.2 Cut Engine Tube | 2 | 5/26/20XX | 5/26/20XX |  |
| -1.2.1 Cut slit of 1/8" @ 1 1/2 inch mark on engine tube | 2 | 5/26/20XX | 5/26/20XX | Cutter #1 |
| -1.3 Glue, Tube, Assemble Hook | 7 | 5/26/20XX | 5/30/20XX |  |
| -1.3.1 Apply thin line of glue completely around engine at 3/4" mark | 2 | 5/26/20XX | 5/26/20XX | Gluer #1 |
| -1.3.2 Position hook per diagram | 2 | 5/26/20XX | 5/30/20XX | Fitter #1 |
| -1.3.3 Insert engine hook into 1/8" slit on engine mount tube | 3 | 5/30/20XX | 5/30/20XX | Fitter #1 |
| -1.4 Assemble Mylar Ring to Tube | 9 | 5/30/20XX | 5/30/20XX |  |
| -1.4.1 Slide mylar ring onto engine mount tube at 3/4" mark | 1 | 5/30/20XX | 5/30/20XX | Fitter #1 |
| -1.4.2 Let dry | 8 | 5/30/20XX | 5/30/20XX |  |
| -1.5 Assemble Yellow Engine Block to Engine Mount Tube | 10 | 5/31/20XX | 5/31/20XX |  |
| -1.5.1 Apply glue inside front of engine mount tube | 1 | 5/31/20XX | 5/31/20XX | Gluer #1 |
| -1.5.2 Insert yellow engine block flush with the right end per diagram | 1 | 5/31/20XX | 5/31/20XX | Fitter #1 |
| -1.5.3 Let dry | 8 | 5/31/20XX | 5/31/20XX |  |
| -1.6 Assemble Centering Rings | 22 | 6/1/20XX | 6/2/20XX |  |
| -1.6.1 Remove centering rings from card with modeling knife | 2 | 6/1/20XX | 6/1/20XX | Cutter #1 |
| -1.6.2 Apply thin line of glue around engine mount tube @ 1/8" mark | 1 | 6/1/20XX | 6/1/20XX | Gluer #1 |
| -1.6.3 Slide notched centering ring onto glued line @ 1/8" mark | 1 | 6/1/20XX | 6/1/20XX | Fitter #1 |
| -1.6.4 Let glue set | 8 | 6/1/20XX | 6/2/20XX |  |
| -1.6.5 Apply thin line of glue to opposite side of notched center ring flush with end of engine mount tube | 1 | 6/2/20XX | 6/2/20XX | Gluer #1 |
| -1.6.6 Slide un-notched centering ring in place over glue flush with end of engine tube mount | 1 | 6/2/20XX | 6/2/20XX | Fitter #1 |
| -1.6.7 Let dry | 8 | 6/2/20XX | 6/2/20XX |  |
| -1.7 Application of Glue Fillets | 10 | 6/5/20XX | 6/5/20XX |  |
| -1.7.1 Apply glue fillets to both sides of centering rings for reinforcement | 2 | 6/5/20XX | 6/5/20XX | Gluer #1 |
| -1.7.2 Let dry | 8 | 6/5/20XX | 6/5/20XX |  |
| 2.0 FIN PREPARATION | 30 | 5/22/20XX | 5/25/20XX |  |
| -2.1 Sand/Cut Fins | 8 | 5/22/20XX | 5/22/20XX |  |
| -2.1.1 Sand laser cut balsa sheet w/ fine sandpaper | 8 | 5/22/20XX | 5/22/20XX | Sander-I #1 |
| -2.2 Cutting Out Fins | 12 | 5/23/20XX | 5/24/20XX |  |
| 2.2.1 Cut out fin #1 w/ modeling knife | 3 | 5/23/20XX | 5/23/20XX | Cutter #2 |
| 2.2.2 Cut out fin #2 w/ modeling knife | 3 | 5/23/20XX | 5/23/20XX | Cutter #2 |
| 2.2.3 Cut out fin #3 w/ modeling knife | 3 | 5/23/20XX | 5/24/20XX | Cutter #2 |
| 2.2.4 Cut out fin #4 w/ modeling knife | 3 | 5/24/20XX | 5/24/20XX | Cutter #2 |
| -2.3 Stack and Sand Fins | 10 | 5/24/20XX | 5/25/20XX |  |
| -2.3.1 Stack fins | 2 | 5/24/20XX | 5/24/20XX | Fitter #2 |
| -2.3.2 Sand edges of fins | 8 | 5/24/20XX | 5/25/20XX | Sander-I #1 |
| 3.0 MARK FIN AND LAUNCH LUG LINES | 33 | 5/22/20XX | 5/30/20XX |  |
| -3.1 Cut - Tape | 13 | 5/22/20XX | 5/25/20XX |  |
| -3.1.1 Cut out tube marking guide | 2 | 5/22/20XX | 5/22/20XX | Cutter #3 |
| -3.1.2 Tape tube marking guide around body tube | 3 | 5/23/20XX | 5/23/20XX | Fitter #3 |
| -3.1.3 Mark body tube at arrows | 4 | 5/23/20XX | 5/23/20XX | Draftsman #2 |
| -3.1.4 Mark launch lug line as LL on body tube | 4 | 5/24/20XX | 5/25/20XX | Draftsman #2 |
| -3.2 Remove Guide, Connect Fins and Lug Lines, Extend LL Line | 16 | 5/25/20XX | 5/30/20XX |  |
| -3.2.1 Remove tube marking guide from body tube | 4 | 5/25/20XX | 5/25/20XX | Fitter #3 |
| -3.2.2 Connect fins using door frame | 4 | 5/25/20XX | 5/26/20XX | Fitter #3 |
| -3.2.3 Connect launch lug lines using door frame | 8 | 5/26/20XX | 5/30/20XX | Fitter #3 |
| -3.3 Extend Launch Lug Line | 4 | 5/30/20XX | 5/30/20XX |  |
| -3.3.1 Extend launch lug line 3 3/4" from end of tube | 4 | 5/30/20XX | 5/30/20XX | Draftsman #2 |
| 4.0 INSERTING ENGINE MOUNT | 43 | 6/6/20XX | 6/9/20XX |  |
| -4.1 Mark Inside of Tube @ 5/8" Where LL is | 7 | 6/6/20XX | 6/6/20XX |  |
| -4.1.1 Measure inside tube to 5/8" position on tube | 4 | 6/6/20XX | 6/6/20XX | Draftsman #1 |
| -4.1.2 Mark inside tube at 5/8" | 3 | 6/6/20XX | 6/6/20XX | Draftsman #1 |
| -4.2 Glue Tube | 5 | 6/6/20XX | 6/7/20XX |  |
| -4.2.1 Measure inside rear of body tube to 1 3/4" position on tube | 3 | 6/6/20XX | 6/7/20XX | Draftsman #1 |
| -4.2.2 Use finger to smear glue 1 3/4" inside rear of body tube along LL | 2 | 6/7/20XX | 6/7/20XX | Gluer #1 |
| -4.3 Assemble Engine Hook | 18 | 6/7/20XX | 6/8/20XX |  |
| -4.3.1 Align engine hook with LL line | 5 | 6/7/20XX | 6/8/20XX | Fitter #1 |
| -4.3.2 Insert engine mount into body tube until centering ring is even w/ the 5/8" glue mark | 5 | 6/8/20XX | 6/8/20XX | Fitter #1 |
| -4.3.3 Let dry | 8 | 6/8/20XX | 6/8/20XX |  |
| -4.4 Gluing Center Body Ring | 13 | 6/9/20XX | 6/9/20XX |  |
| -4.4.1 Locate scrap piece of balsa to apply glue | 1 | 6/9/20XX | 6/9/20XX | Fitter #1 |
| -4.4.2 Apply glue to centering/body tube joint | 4 | 6/9/20XX | 6/9/20XX | Gluer #1 |
| -4.4.3 Let dry | 8 | 6/9/20XX | 6/9/20XX |  |
| 5.0 ATTACH FINS | 73 | 6/12/20XX | 6/16/20XX |  |
| -5.1 Attach Fin #1 | 10 | 6/12/20XX | 6/13/20XX |  |
| -5.1.1 Apply thin layer of glue to edge of fin | 3 | 6/12/20XX | 6/12/20XX | Gluer #3 |
| -5.1.2 Allow to dry (1 minute for model) | 1 | 6/12/20XX | 6/12/20XX |  |
| -5.1.3 Apply second layer of glue to edge of fin | 2 | 6/12/20XX | 6/12/20XX | Gluer #3 |
| -5.1.4 Attach fin to body tube along one of fin lines flush w/ end | 4 | 6/12/20XX | 6/13/20XX | Fitter #3 |
| -5.2 Attach Fin #2 | 10 | 6/12/20XX | 6/13/20XX |  |
| -5.2.1 Apply thin layer of glue to edge of fin #2 | 3 | 6/12/20XX | 6/12/20XX | Gluer #2 |
| -5.2.2 Allow to dry (1 minute for model) | 1 | 6/12/20XX | 6/12/20XX |  |
| -5.2.3 Apply second layer of glue to edge of fin #2 | 2 | 6/12/20XX | 6/12/20XX | Gluer #2 |
| -5.2.4 Attach fin #2 to body tube along one of fin lines flush w/ end | 4 | 6/12/20XX | 6/13/20XX | Fitter #2 |
| -5.3 Attach Fin #3 | 10 | 6/12/20XX | 6/13/20XX |  |
| -5.3.1 Apply thin layer of glue to edge of fin #3 | 3 | 6/12/20XX | 6/12/20XX | Gluer #1 |
| -5.3.2 Allow to dry (1 minute for model) | 1 | 6/12/20XX | 6/12/20XX |  |
| -5.3.3 Apply second layer of glue to edge of fin #3 | 2 | 6/12/20XX | 6/12/20XX | Gluer #1 |
| -5.3.4 Attach fin #3 to body tube along one of fin lines flush w/ end | 4 | 6/12/20XX | 6/13/20XX | Fitter #1 |
| -5.4 Attach Fin #4 | 10 | 6/12/20XX | 6/13/20XX |  |
| -5.4.1 Apply thin layer of glue to edge of fin #4 | 3 | 6/12/20XX | 6/12/20XX | Gluer #4 |
| -5.4.2 Allow to dry (1 minute for model) | 1 | 6/12/20XX | 6/12/20XX |  |
| -5.4.3 Apply second layer of glue to edge of fin #4 | 2 | 6/12/20XX | 6/12/20XX | Gluer #4 |
| -5.4.4 Attach fin #4 to body tube along one of fin lines flush w/ end | 4 | 6/12/20XX | 6/13/20XX | Fitter #4 |
| -5.5 Check Fin Alignment | 16 | 6/13/20XX | 6/15/20XX |  |
| -5.5.1 Check fin #1 alignment as shown in diagram | 4 | 6/13/20XX | 6/13/20XX | Draftsman #1 |
| -5.5.2 Check fin #2 alignment as shown in diagram | 4 | 6/13/20XX | 6/14/20XX | Draftsman #2 |
| -5.5.3 Check fin #3 alignment as shown in diagram | 4 | 6/14/20XX | 6/14/20XX | Draftsman #1 |
| -5.5.4 Check fin #4 alignment as shown in diagram | 4 | 6/14/20XX | 6/15/20XX | Draftsman #2 |
| -5.6 Allow Glue to Dry | 17 | 6/15/20XX | 6/16/20XX |  |
| -5.6.1 Let glue set | 5 | 6/15/20XX | 6/15/20XX |  |
| -5.6.2 Stand rocket on end | 4 | 6/15/20XX | 6/16/20XX | Fitter #1 |
| -5.6.3 Let glue dry completely | 8 | 6/16/20XX | 6/16/20XX |  |
| 6.0 ATTACH SHOCK CORD | 44 | 5/22/20XX | 5/26/20XX |  |
| -6.1 Cut Out Shock Cord Mount | 5 | 5/22/20XX | 5/22/20XX |  |
| -6.1.1 Cut out shock cord from front page | 5 | 5/22/20XX | 5/22/20XX | Cutter #1 |
| -6.2 First Glue Application | 12 | 5/22/20XX | 5/24/20XX |  |
| -6.2.1 Attach shock cord to shock cord mount | 4 | 5/22/20XX | 5/23/20XX | Fitter #5 |
| -6.2.2 Apply glue to shock cord mount | 4 | 5/23/20XX | 5/23/20XX | Gluer #4 |
| -6.2.3 Fold edge of shock cord mount forward over glued shock cord | 4 | 5/23/20XX | 5/24/20XX | Fitter #5 |
| -6.3 Second Glue Application | 8 | 5/24/20XX | 5/25/20XX |  |
| -6.3.1 Apply glue to shock cord mount | 4 | 5/24/20XX | 5/24/20XX | Gluer #4 |
| -6.3.2 Fold forward again-see diagram for clarification | 4 | 5/24/20XX | 5/25/20XX | Fitter #5 |
| -6.4 Squeeze and Hold | 6 | 5/25/20XX | 5/25/20XX |  |
| -6.4.1 Squeeze shock cord/shock cord mount tightly | 2 | 5/25/20XX | 5/25/20XX | Gluer #4 |
| -6.4.2 Hold for 1 minute | 4 | 5/25/20XX | 5/25/20XX | Gluer #4 |
| -6.5 Attaching Shock Cord Mount | 13 | 5/25/20XX | 5/26/20XX |  |
| -6.5.1 Glue mount 1" inside body tube | 4 | 5/25/20XX | 5/26/20XX | Gluer #4,Fitter #5 |
| -6.5.2 Hold until glue sets | 1 | 5/26/20XX | 5/26/20XX | Gluer #4 |
| -6.5.3 Let dry completely | 8 | 5/26/20XX | 5/26/20XX |  |
| 7.0 ASSEMBLE NOSE CONE | 16 | 5/22/20XX | 5/23/20XX |  |
| -7.1 Glue Nose Cone | 16 | 5/22/20XX | 5/23/20XX |  |
| -7.1.1 Apply plastic cement to inside rim of nose cone | 4 | 5/22/20XX | 5/22/20XX | Gluer #5 |
| -7.1.2 Press nose cone insert into place over plastic cement inside of nose cone rim | 4 | 5/22/20XX | 5/22/20XX | Fitter #2 |
| -7.1.3 Let dry completely | 8 | 5/22/20XX | 5/23/20XX |  |
| 8.0 ATTACH PARACHUTE/SHOCK CORD | 18 | 5/30/20XX | 6/2/20XX |  |
| -8.1 Attach Lines | 7 | 5/30/20XX | 5/31/20XX |  |
| -8.1.1 Pass shroud line on parachute through eyelet | 7 | 5/30/20XX | 5/31/20XX | Fitter #1 |
| -8.2 Attach Parachute | 5 | 5/31/20XX | 6/1/20XX |  |
| -8.2.1 Pass parachute through loop in shroud-look to diagram for clarification | 5 | 5/31/20XX | 6/1/20XX | Fitter #1 |
| -8.3 Tie Lines | 6 | 6/1/20XX | 6/2/20XX |  |
| -8.3.1 Tie shock cord to nose cone using a double knot | 6 | 6/1/20XX | 6/2/20XX | Fitter #1 |
| 9.0 ATTACH LAUNCH LUG | 32 | 6/19/20XX | 6/22/20XX |  |
| -9.1 Glue Launch Lines | 4 | 6/19/20XX | 6/19/20XX |  |
| -9.1.1 Glue LL centered onto LL line on rocket body | 4 | 6/19/20XX | 6/19/20XX | Gluer #1 |
| -9.2 Application of Glue Fillets | 28 | 6/19/20XX | 6/22/20XX |  |
| -9.2.1 Apply glue fillets along launch lug | 4 | 6/19/20XX | 6/19/20XX | Gluer #1 |
| -9.2.2 Apply glue fillets along fin/body tube joints | 12 | 6/20/20XX | 6/21/20XX | Gluer #1 |
| -9.2.3 Smooth each fillet with finger | 4 | 6/21/20XX | 6/21/20XX | Gluer #1 |
| -9.2.4 Let glue dry completely | 8 | 6/21/20XX | 6/22/20XX |  |
| 10.0 PAINTING THE ROCKET | 64 | 6/22/20XX | 6/29/20XX |  |
| -10.1 Apply First Coat | 16 | 6/22/20XX | 6/23/20XX |  |
| -10.1.1 Spray rocket with white primer | 8 | 6/22/20XX | 6/22/20XX | Painter-I #1 |
| -10.1.2 Let dry | 8 | 6/22/20XX | 6/23/20XX |  |
| -10.2 Sand | 8 | 6/23/20XX | 6/23/20XX |  |
| -10.2.1 Sand entire rocket | 8 | 6/23/20XX | 6/23/20XX | Sander-I #1,Sander-I #2,Sander-II #1,Sander-II #2 |
| -10.3 Apply Final Coat | 40 | 6/26/20XX | 6/29/20XX |  |
| -10.3.1 Spray completed rocket with white second coat of primer | 8 | 6/26/20XX | 6/26/20XX | Painter-II #1,Painter-II #2 |
| -10.3.2 Let dry | 8 | 6/26/20XX | 6/27/20XX |  |
| -10.3.3 Spray nose cone with copper paint | 16 | 6/27/20XX | 6/28/20XX | Painter-II #1,Painter-II #2 |
| -10.3.4 Let dry | 8 | 6/28/20XX | 6/29/20XX |  |
| 11.0 APPLICATION OF DECALS | 35 | 6/29/20XX | 7/6/20XX |  |
| -11.1 Apply First Decal | 5 | 6/29/20XX | 6/29/20XX |  |
| -11.1.1 Remove first decal from back sheet | 1 | 6/29/20XX | 6/29/20XX | Draftsman #1 |
| -11.1.2 Place on rocket where indicated | 3 | 6/29/20XX | 6/29/20XX | Draftsman #2 |
| -11.1.3 Rub decal to remove bubbles | 1 | 6/29/20XX | 6/29/20XX | Draftsman #1 |
| -11.2 Apply Second Decal | 5 | 6/29/20XX | 6/30/20XX |  |
| -11.2.1 Remove second decal from backing sheet | 1 | 6/29/20XX | 6/29/20XX | Draftsman #1 |
| -11.2.2 Place on rocket where indicated | 3 | 6/29/20XX | 6/30/20XX | Draftsman #2 |
| -11.2.3 Rub decal to remove bubbles | 1 | 6/30/20XX | 6/30/20XX | Draftsman #1 |
| -11.3 Apply Third Decal | 5 | 6/30/20XX | 6/30/20XX |  |
| -11.3.1 Remove third decal from backing sheet | 1 | 6/30/20XX | 6/30/20XX | Draftsman #1 |
| -11.3.2 Place on rocket where indicated | 3 | 6/30/20XX | 6/30/20XX | Draftsman #2 |
| -11.3.3 Rub decal to remove bubbles | 1 | 6/30/20XX | 6/30/20XX | Draftsman #1 |
| -11.4 Apply Fourth Decal | 5 | 6/30/20XX | 7/3/20XX |  |
| -11.4.1 Remove fourth decal from backing sheet | 1 | 6/30/20XX | 6/30/20XX | Draftsman #1 |
| -11.4.2 Place on rocket where indicated | 3 | 7/3/20XX | 7/3/20XX | Draftsman #2 |
| -11.4.3 Rub decal to remove bubbles | 1 | 7/3/20XX | 7/3/20XX | Draftsman #1 |
| -11.5 Apply Fifth Decal | 5 | 7/3/20XX | 7/5/20XX |  |
| -11.5.1 Remove fifth decal from backing sheet | 1 | 7/3/20XX | 7/3/20XX | Draftsman #1 |
| -11.5.2 Place on rocket where indicated | 3 | 7/3/20XX | 7/3/20XX | Draftsman #2 |
| -11.5.3 Rub decal to remove bubbles | 1 | 7/5/20XX | 7/5/20XX | Draftsman #1 |
| -11.6 Apply Sixth Decal | 5 | 7/5/20XX | 7/5/20XX |  |
| -11.6.1 Remove sixth decal from backing sheet | 1 | 7/5/20XX | 7/5/20XX | Draftsman #1 |
| -11.6.2 Place on rocket where indicated | 3 | 7/5/20XX | 7/5/20XX | Draftsman #2 |
| -11.6.3 Rub decal to remove bubbles | 1 | 7/5/20XX | 7/5/20XX | Draftsman #1 |
| -11.7 Apply Seventh Decal | 5 | 7/5/20XX | 7/6/20XX |  |
| -11.7.1 Remove seventh decal from backing sheet | 1 | 7/5/20XX | 7/5/20XX | Draftsman #1 |
| -11.7.2 Place on rocket where indicated | 3 | 7/5/20XX | 7/6/20XX | Draftsman #2 |
| -11.7.3 Rub decal to remove bubbles | 1 | 7/6/20XX | 7/6/20XX | Draftsman #1 |
| 12.0 APPLYING CLEAR COAT | 16 | 7/6/20XX | 7/7/20XX |  |
| -12.1 Apply Clear Coat to Entire Rocket | 16 | 7/6/20XX | 7/7/20XX |  |
| -12.1.1 Apply clear coat to entire rocket | 8 | 7/6/20XX | 7/7/20XX | Painter-II #1 |
| -12.1.2 Dry completely | 8 | 7/7/20XX | 7/7/20XX |  |
| 13.0 DISPLAY NOZZLE ASSEMBLY | 32 | 7/10/20XX | 7/13/20XX |  |
| -13.1 Spray Nozzle Base White | 18 | 7/10/20XX | 7/11/20XX |  |
| -13.1.1 Paint nozzle #1 w/ silver paint pen | 2.5 | 7/10/20XX | 7/10/20XX | Painter-I #1 |
| -13.1.2 Paint nozzle #2 w/ silver paint pen | 2.5 | 7/10/20XX | 7/10/20XX | Painter-I #1 |
| -13.1.3 Paint nozzle #3 w/ silver paint pen | 2.5 | 7/10/20XX | 7/10/20XX | Painter-I #1 |
| -13.1.4 Paint nozzle #4 w/ silver paint pen | 2.5 | 7/10/20XX | 7/11/20XX | Painter-I #1 |
| -13.1.5 Allow to dry | 8 | 7/11/20XX | 7/11/20XX |  |
| -13.2 Apply Glue | 14 | 7/12/20XX | 7/13/20XX |  |
| -13.2.1 Apply glue to tab on nozzle #1 | 1.5 | 7/12/20XX | 7/12/20XX | Gluer #1 |
| -13.2.2 Place nozzle #1 into hole on base | 2 | 7/12/20XX | 7/12/20XX | Fitter #1 |
| -13.2.3 Apply glue to tab on nozzle #2 | 1.5 | 7/12/20XX | 7/12/20XX | Gluer #1 |
| -13.2.4 Place nozzle #2 into hole on base | 2 | 7/12/20XX | 7/12/20XX | Fitter #1 |
| -13.2.5 Apply glue to tab on nozzle #3 | 1.5 | 7/12/20XX | 7/13/20XX | Gluer #1 |
| -13.2.6 Place nozzle #3 into hole on base | 2 | 7/13/20XX | 7/13/20XX | Fitter #1 |
| -13.2.7 Apply glue to tab on nozzle #4 | 1.5 | 7/13/20XX | 7/13/20XX | Gluer #1 |
| -13.2.8 Place nozzle #4 into hole on base | 2 | 7/13/20XX | 7/13/20XX | Fitter #1 |
| 14.0 ROCKET PREFLIGHT | 42 | 7/13/20XX | 7/20/20XX |  |
| 14.1 Prepare | 13 | 7/13/20XX | 7/17/20XX |  |
| -14.1.1 Remove nose cone from rocket | 6 | 7/13/20XX | 7/14/20XX | Fitter #1 |
| -14.1.2 Locate recovery wadding | 1 | 7/14/20XX | 7/14/20XX | Fitter #1 |
| -14.1.3 Insert 4–5 loosely crumpled squares of recovery wadding | 6 | 7/14/20XX | 7/17/20XX | Fitter #1 |
| 14.2 Spike | 4 | 7/17/20XX | 7/17/20XX |  |
| -14.2.1 Pull parachute into a spike-see diagram for clarification | 4 | 7/17/20XX | 7/17/20XX | Fitter #1 |
| 14.3 Fold | 4 | 7/17/20XX | 7/18/20XX |  |
| -14.3.1 Fold parachute according to diagram | 4 | 7/17/20XX | 7/18/20XX | Fitter #1 |
| 14.4 Roll | 4 | 7/18/20XX | 7/18/20XX |  |
| -14.4.1 Roll parachute according to diagram | 4 | 7/18/20XX | 7/18/20XX | Fitter #1 |
| 14.5 Re-Insert | 17 | 7/18/20XX | 7/20/20XX |  |
| -14.5.1 Wrap lines loosely around rolled parachute—see diagram for clarification | 5 | 7/18/20XX | 7/19/20XX | Fitter #1 |
| -14.5.2 Insert parachute into body tube of rocket | 6 | 7/19/20XX | 7/20/20XX | Fitter #1 |
| -14.5.3 Insert shock cord into body tube of rocket | 2 | 7/20/20XX | 7/20/20XX | Fitter #1 |
| -14.5.4 Insert nose cone into body tube of rocket | 4 | 7/20/20XX | 7/20/20XX | Fitter #1 |
| 15.0 PREPARE FOR TEST LAUNCH | 32 | 7/21/20XX | 7/26/20XX |  |
| -15.1 Insert Engine | 32 | 7/21/20XX | 7/26/20XX |  |
| -15.1.1 Remove engine | 10 | 7/21/20XX | 7/24/20XX | Engineer #1 |
| -15.1.2 Insert tip to touch propellant | 10 | 7/24/20XX | 7/25/20XX | Engineer #1 |
| -15.1.3 Insert engine into rocket | 12 | 7/25/20XX | 7/26/20XX | Engineer #1 |

# 3.0 Cost Management Plan

## Introduction

# The Gauchito Rocket Project Cost Management Plan covers defining cost estimates, creating the cost baseline, and managing the cost of the project. Because the project is of short duration, requiring intense workloads during the schedule in order to produce the deliverables, cost will be critical to manage and to control in order to meet the definitive budget.

# The overall labor estimate is $19,950.

# The estimated at completion (EAC) is $50,150 for the 10-week schedule. The EAC includes all direct labor costs, as well as material and equipment costs. The details of cost management for the Gauchito project are covered below.

# Equipment and custom parts

# Equipment and material order dates

# Precision formats

# How the cost estimate is developed

# Precision formats

# Personnel usage by time period labor expenditure on the project (Reference Appendix E)

# How cost baseline and budget was developed (Reference Appendix H)

# Identify when personnel are utilized and differences with the cost budget

# Reporting formats for cost management

# Cost control and managing process

# Cost constraints

# Cost assumptions

# The constraints and assumptions are specific to cost management of the project. The overall project constraints and assumptions also apply to cost management.

## Equipment and Custom Parts

The Gauchito project requires a complete rocket assembly and specialty hybrid engines. These parts must be purchased and on-site no later than the Friday before the project start date to ensure work can start on schedule. The risk management plan addresses response if some material and equipment is not received by that date. For example, if the paint is not received, it would have no cost impact because it is not used at project start, and it can be reordered and delivered before it is needed. The previous order would be cancelled so double charges are not incurred.

The cost for materials, equipment, and custom parts is included in the first week, as shown in the cost baseline in Appendix H, page 125. A breakout is shown below.

| # Item | # Cost | # Purchase Date |
| --- | --- | --- |
| # Rocket Assembly – all standard rocket components, including rocket engine wadding, parachute, nose cone, and rocket body | # $15,000 | # Due at project start |
| # Hybrid Engines – A3-4T (4 @ $2,500 each) | # $10,000* | # Due at project start |
| # Delivery costs | # $125 |  |
| # Materials as specified in the assembly construction plan, including pens, pencils, glue, scissors, engine wadding, paint, tape measure, string, sandpaper, and modeling knife | # $5,000 | # Due at project start |

# * The original cost estimates included the hybrid engines, but the cost increased after procurement evaluation and determining the actual cost. The difference is $5,000 between the scope estimated budget and the cost baseline provided in this plan.

## Equipment and Material Order Dates

All equipment, including the specialty hybrid engines, is to be ordered at least 12 days prior to project start. The hybrid engines are not required until the last week of the project. However, in order to validate compatibility with the rocket, they are due at the same time as other materials and equipment, the week before project start.

The project plan and cost approval will include authorization to order the equipment before project start and allocate funds to the materials and equipment. Though the material and equipment will be ordered prior to project start, they are not allocated to the baseline until after receipt, so they are applied to the cost expenditures for the first week of the project. They are included in the overall EAC.

3.1 Precision Formats

3.1.1 Cost estimation for WBS by skill set:

- The cost estimates are in whole hours, rounded to the nearest hour.

- The labor rates are rounded to the nearest $5.00 increment and are shown at the bottom of the cost estimate spreadsheet.

3.1.2 Baseline budget and EAC:

- The material and equipment cost is rounded up to the nearest $100.00.

- The labor rate for employees is a blended rate.

- The costs are reflected by week plus cumulative for all weeks to calculate the EAC.

## 3.2 How the Cost Estimate is Developed

# The Gauchito project manager and team members met to review the product description, project charter, and preliminary scope statement. These documents provided an overall definition of the goal, the deliverables, initial rough order cost and budget estimates, and the project time frame.

# The team reviewed the work breakdown structure, initial staffing resource needs, scheduled durations for each deliverable, milestones, and the target budget. These detailed data provided the basis upon which to refine resources needed for each WBS work package and to define costs for each type of resource skill set (e.g., fitters for the project).

# In order to arrive at a complete cost estimate, the project manager and team met with subject matter experts (SMEs) for each of the disciplines (e.g., fitters, draftsmen, and other skill types). This proved invaluable in defining the activities needed to accomplish each work package task, if it was not predefined. The SMEs and project team reviewed the Gauchito Rocket Construction Plan (in Appendix C) as a reference to ensure all activities were included for cost estimation.

# In addition, the project manager reviewed existing cost estimates for the previously concluded Generic Estes project. While that project was not of the same size and scope of the Gauchito project, it provided useful cost information and lessons learned for the cost estimates.

# The project manager gathered the estimation of time, in man-hours, needed by each skill set to complete each work package. The total time for each deliverable, and for all deliverables, was calculated, as well as total time for each skill set (e.g., fitter). The hourly rate for each skill set was applied to the resource time estimates to arrive at the total project labor cost.

# No overhead resources were included in the cost estimate. Though the duration estimate number of hours includes “dummy” time for drying the glue, it is not included in any cost estimates.

## Personnel Usage by Time Period Labor Expenditure On Project

# Appendix C shows the personnel skill set needed for the project and when they will be used on the project. The resource skill sets and time estimates for each are applied to each WBS work package. This duration estimate is part of the cost estimate spreadsheet.

# Duration smoothing was not applied because the tasks are so well defined, and SSTC has previous experience form the Generic Estes project. No optimistic schedule was determined. A consideration for a pessimistic schedule was that the new hybrid engines are unknown technology in conjunction with the standard rocket kit assembly. However, the team determined that the task would take no more time than installing standard rockets.

## 3.3 How the Cost Baseline and Budget is Developed

# The total labor costs from the duration and cost estimate chart, and the material and equipment costs, were input to create the cost baseline and budget. Labor costs: The total costs from the cost estimation results—the personnel by WBS work package—have been input as part of the development of the budget and cost baseline. The resource requirements for each week were determined using resource staffing information per the staffing management plan. The resources needed to complete the work packages scheduled for the week have been input to the spend plan and total costs applied to the week based on blended labor rates. The labor cost was based upon a blended rate of $35 per hour for employees. The contracted labor cost was based upon a rate of $50 per hour. The total labor cost is reflected in the appendices.

# All cost of material and equipment is included in the baseline. The materials and equipment costs have been provided per the procurement management plan and will be purchased for delivery the week before project start. Therefore, those costs are reflected during the first week of the project. The difference from the preliminary budget is $5,000. However, there is no difference between the definitive budget and cost baseline because the costs are included.

# The baseline budget EAC is targeted to within –5% and +10 of the budget at completion (BAC).

## Identify When Personnel Are Utilized and Differences with the Cost Budget

# The baseline is in Appendix H. The baseline is shown in increments by time period reporting, which is weekly, showing the labor costs per each week as well as the material and equipment cost per week.

# The costs are reflected in an S-curve chart showing the cumulative budgeted costs weekly and showing the total budgeted cost, EAC.

# The spend plan for personnel is shown in Appendix H as part of the input to creating the cost baseline and budget. The input to the spend plan is the duration estimates and costs applied to each resource type, along with the schedule. The cost is shown weekly for each resource needed to complete the work scheduled for that week.

# The differences between the spend plan costs and the original cost budget estimates reflect a slight increase due to expert evaluation of the amount of time needed to complete each task.

## Reporting Formats for Cost Reports

The project manager will report weekly on cost and schedule status for the previous week. The report will be distributed to SSTC executive management, the sponsor, finance, De Leon and Associates customer contacts, and functional managers with staff assigned to the project. The report will be briefed at the weekly project meeting. These costs are based on the budgeted cost of work scheduled (BCWS) in the baseline cost in Appendix H. An example report format follows, and it will use earned value management to provide actual costs and work performed against the BCWS (the planned value [PV]). The BCWS/baseline costs, the actual costs, and the cost of amount of work performed will be plotted on the S-curve chart, similar to the graphic shown. The amount of work performed may reflect either a deliverable or the WBS tasks that should have been completed in support of a deliverable. The cost variance (earned value – actual cost) and the schedule variance (earned value – planned value) are included, along with explanations for the variance.

# EXAMPLE Cost Management Report: Figure 3-1

# Gauchito Project Cost Management Report                                              Date:

# The Gauchito Project EAC is ____________.

# The Gauchito Project BAC is ____________.

# Week #: _______

# Earned value for cost of work actually performed (BCWP or EV):

# Actual costs for the week (ACWP or AC):

# Cost variance (EV – AC):

# Explanation and corrective action, if needed:

# Earned value for cost of work actually performed (BCWP or EV):

# Budgeted cost of work scheduled (BCWS or PV):

# Schedule variance (EV – PV):

# Explanation and corrective action, if needed:

# Figure 4-2 Cost Baseline Cumulative S-Curve Space Systems

## 3.5 Cost Control

# The project manager will use the weekly time reporting and rollup costs reported for each account/WBS to total the amount spent for the week. This amount will be calculated into the actual costs for the week. The project manager will use the weekly status reports to determine which deliverables and work packages were completed.

# If the labor actual cost exceeds the value of the work completed, compared to the cost baseline, the project manager will determine reasons for the difference. For example, if Deliverable 1 is completed during Week 1 of the project, with an earned value of $1,000, and the actual labor costs for the week total $1,200, the variance is negative $200. One reason may be that tasks in the work packages scheduled for Week 1 took longer than expected due to unforeseen problems.

# One area to examine is to ensure that additional work was not performed. If problems arose, then the project team will identify those problem areas and a course of action to see if the time can be made up and if costs will not increase. This is especially critical if the problem could occur in future work packages for the project.

# If the earned value for Deliverable 1 completed in Week 1 is $1,000, and the planned value was to be $1,200, then there is a negative $200 in schedule. This means some tasks may be behind schedule. The project manager will use the same approach as for cost variances in determining root cause and course of action.

# All changes to scope, schedule, contracts, or purchases will follow the overall change control process outlined in the scope management plan. Proposed changes will be presented to the configuration control board, along with the associated cost changes to the baseline cost.

# If costs are increased due to finding that the tasks take longer than expected, the project manager and contracts/procurement management will determine a course of action based on the contract type. The project manager will consult with functional managers to define alternate approaches.

# As approved changes occur, updates will be applied to the cost estimates, personnel usage, and material and equipment changes. The project manager will revise the baseline with a new EAC, as well as revise this cost management plan. The changes will be applied to other impacted plans as necessary.

# To enable the project manager to track costs and changes, corporate databases for time reporting, issues, and risks will be used. In addition, standard corporate guidelines for cost accounting, procurement, contracts, and earned value management will be followed.

## Cost Constraints

# The fitter positions will be outsourced. This increases the labor rates to contractor rates, used in cost estimation.

# The Memorial Day and Independence Day holidays fall within the project start/finish dates.

## Cost Assumptions

# Labor is calculated based on man-hour rates.

# Labor rates have been provided as static for this project. No increases are planned in the 10-week project time frame. The blended rate used is standard across the corporation. Contractor labor rates are negotiated per the outsourcing contract and are static for the project's duration.

# No overtime hours and rates for resources are included in the cost estimates.

# No cost estimates are applied for Memorial Day and Independence Day. Fitters are not paid for that day, and employee time off is part of overhead costs.

Project Name: Ansari X Prize Gauchito Rocket

Product-Process: Quality

Prepared By: Thomas Jones

Project Quality Plan Version Control

| Version | Date | Author | Change Description |
| --- | --- | --- | --- |
| 1.0 | 4/30/06 | Thomas Jones | Initial |

4.0 Quality Management Plan

# 4.1 Project Quality Plan Purpose

The purpose of this plan is to ensure that the rocket is built to the specifications set by the customer. Customer satisfaction with the workmanship, cost, and final delivery of the final product is key to achieving the goal of follow-on work of future contracts.

# Quality Management Method

The construction material used for this project has been handpicked by the customer. It will only be inspected for damage that may have occurred during shipping. The construction processes have also been written by the customer. Quality for this project will only consist of ensuring that the construction processes have been followed and whether there is any room for improvement.

## 4.2 Quality Plan Processes

## Quality Assurance

It is the policy of Space SystemsTechnology CorporationTechnology Corporation   and its elements to develop, integrate, and implement QA and QC practices to assure delivery of quality products and services that meet or exceed customer needs and expectations in accordance with applicable laws, policies, technical criteria, schedules, and budgets. Adherence to quality principles and established QA and QC practices is integral to the roles and responsibilities of all SSTC’s elements and functions.

Quality standards have been set by the customer in the kit assembly directions given to the Gauchito rocket project team. The QA team will inspect each deliverable as milestones are reached. Checklists will be developed using the kit directions for each station assembling a section of the rocket. The checklist will simply ensure each step in the assembly process is done in accordance with the customer’s instructions.

Quality Control

The checklists at each station will be picked up by the QA team during the inspection of the deliverable and given to the customer with training documentation.

Project Deliverables and Processes Acceptance Criteria

All deliverables will be constructed according to kit instructions.

1.0 ASSEMBLE ENGINE MOUNT

2.0 FIN PREPARATION

3.0 MARK FIN AND LAUNCH LUG LINES

4.0 INSERTING ENGINE MOUNT

5.0 ATTACH FINS

6.0 ATTACH SHOCK CORD

7.0 ASSEMBLE NOSE CONE

8.0 ATTACH PARACHUTE/SHOCK CORD

9.0 ATTACH LAUNCH LUG

10.0 PAINTING THE ROCKET

11.0 APPLICATION OF DECALS

12.0 APPLYING CLEAR COAT

13.0 DISPLAY NOZZLE ASSEMBLY

14.0 ROCKET PREFLIGHT

15.0 PREPARE FOR TEST LAUNCH

Project Overview

This project will address design consideration of the Gauchito rocket. The rocket’s design, launch, and test results can be observed using a 7/8 scale of the full-sized rocket. This approach provides a valid measurement of the rocket’s success without the time and expense necessary to build a full-sized rocket. This will also help in the identification, mitigation, and avoidance of risk to the space development program. This project is being undertaken to show that our company has the ability to produce a reliable test product that accurately duplicates the final full-sized rocket. To do this, we will deliver the completed 7/8 scale rocket 3 days after the assembly is completed to Peterson AFB test launch site.

See appendix for WBS, schedule, risks, and cost.

## Quality Standards

Rocket parts included in the kit have been inspected. These parts are of acceptable quality and grade for this project. The 4 solid fuel rockets being installed on the 7/8th scaled rocket have been engineered and tested to produce similar thrust as the 4 hybrid engines on the full-scale rocket.

## Quality Tools

Audits of all deliverables will be made by a QA team member. Checklists will be verified and signed by the fitter, draftsman, gluer, or sander. The checklist will be verified and signed by the QA team member and turned over to the customer with the training documentation.

Quality Manager’s Responsibilities

Thomas Jones has been assigned quality manager and has the responsibility for:

- Specifying how the quality assurance processes should be applied

- Specifying how the quality control procedures should be applied

- Specifying the continuous process improvement for the project

- Defining criteria for the effective execution of key project activities, processes, and deliverables

- Defining quality management responsibilities for the project

- Identifying or including any checklists or templates that should be used by project team members

- Defining how the project will be audited to ensure compliance with the quality management plan

# Project Quality Assurance

Quality assurance helps to establish if a deliverable is acceptable based on the processes used to create it. Quality assurance processes are used to evaluate overall project performance frequently and to determine that quality reviews were held, deliverables tested, and customer acceptance acquired.

## Quality Assurance Procedures

Quality has been designed into the product. All of the parts used in this rocket project have been handpicked by the customer for the 7/8th scaled rocket. Although the assembly procedures were written by the customer, they will be monitored by QA team members looking for ways to improve the process of gluing, sanding, and painting through the use of better tools or material. Staff and subcontractors with knowledge of the processes being used will be asked for recommendations for improvement on the checklists.

Subcontract Fitters—Three of the top fitter contracting companies in the local area have been judged on their previous job performances. The local fitters union has been found to have a reputation for good, reliable work with exceptional employees.

| Contractor | Reliability % | Work Quality | Mistakes |
| --- | --- | --- | --- |
| Local Fitters Union | 100 | 100 | 0 |
| ACME Fitters | 40 | 60 | 25 |
| Fitters-R-Us | 25 | 65 | 25 |

## Project Monitoring Processes

A checklist will be marked off for each of the measurable steps in the construction process. These checklists will be signed off by one of the staff or subcontracted fitters and a QA team member. This will ensure that all steps in the construction process were followed. Staff and subcontractors with knowledge of the processes being used will be asked for recommendations for improvement on the checklists. These recommendations will be passed to management and the customer for consideration in improving the construction of the full-scale rocket.

# Project Quality Control

|  | Step Completed |  |
| --- | --- | --- |
| ASSEMBLE ENGINE MOUNT | YES | NO |
| Mark left end of engine tube @ 1/8’ |  |  |
| Mark from left of engine tube @ ¾’ |  |  |
| Mark from left of engine tube @ 1 ½’ |  |  |
| Cut slit of 1/8’ @ 1 ½ inch mark on engine tube |  |  |
| Glue tube, assemble hook |  |  |
| Apply thin line of glue completely around engine at ¾’ mark |  |  |
| Insert engine hook into 1/8’ slit on engine mount tube |  |  |
| Slide mylar ring onto engine mount tube at 3/4" mark |  |  |
| Glue dry at ¾’ mark |  |  |
| Apply glue inside front of engine mount tube |  |  |
| Yellow engine block flush with the right end per diagram |  |  |
| Let dry |  |  |
| Remove centering rings from card with modeling knife |  |  |
| Apply thin line of glue around engine mount tube @ 1/8" mark |  |  |
| Slide notched centering ring onto glued line @ 1/8" mark |  |  |
| Glue set |  |  |
| Apply thin line of glue to opposite side of notched center ring flush with end of engine mount tube |  |  |
| Slide un-notched centering ring in place over glue flush with end of engine tube mount |  |  |
| Centering rings dry |  |  |
| Apply glue fillets to both sides of centering rings for reinforcement |  |  |
| Centering rings dry |  |  |

Signatures                                                                                       Date

Verifier:   ____________________________________           ______________

QA Team: _____________________________________          ______________

Suggestions for improvement (materials or processes): _____________________ _________________________________________________________________

_________________________________________________________________

_________________________________________________________________

_________________________________________________________________

|  | Step Completed |  |
| --- | --- | --- |
| FIN PREPARATION | YES | NO |
| Sand laser cut balsa sheet w/ fine sandpaper |  |  |
| Cut out fin #1 |  |  |
| Cut out fin #2 |  |  |
| Cut out fin #3 |  |  |
| Cut out fin #4 |  |  |
| Sand edges of fins |  |  |
| FIN PREPARATION |  |  |
| Sand laser cut balsa sheet w/ fine sandpaper |  |  |
| Cut out fin #1 |  |  |
| Cut out fin #2 |  |  |
| Cut out fin #3 |  |  |
| Cut out fin #4 |  |  |
| Sand edges of fins |  |  |
| FIN PREPARATION |  |  |

Signatures                                                                                       Date

Verifier:      ____________________________________           ______________

QA Team: _____________________________________          ______________

Suggestions for improvement (materials or processes): _____________________ _________________________________________________________________

_________________________________________________________________

_________________________________________________________________

_________________________________________________________________

|  | Step Completed |  |
| --- | --- | --- |
| MARK FIN AND LAUNCH LUG LINES | YES | NO |
| Mark body tube at arrows |  |  |
| Mark launch lug line as LL on body tube |  |  |
| Connect fins |  |  |
| Connect launch lug lines |  |  |
| Extend launch lug line 3 ¾” from end of tube |  |  |
| MARK FIN AND LAUNCH LUG LINES |  |  |
| Mark body tube at arrows |  |  |
| Mark launch lug line as LL on body tube |  |  |
| Connect fins |  |  |
| Connect launch lug lines |  |  |
| Extend launch lug line 3 ¾” from end of tube |  |  |
| MARK FIN AND LAUNCH LUG LINES |  |  |
| Mark body tube at arrows |  |  |
| Mark launch lug line as LL on body tube |  |  |
| Connect fins |  |  |

Signatures                                                                                       Date

Verifier:   ____________________________________             ______________

QA Team: _____________________________________          ______________

Suggestions for improvement (materials or processes): _____________________ _________________________________________________________________

_________________________________________________________________

|  | Step Completed |  |
| --- | --- | --- |
| INSERTING ENGINE MOUNT | YES | NO |
| Mark inside tube at 5/8" |  |  |
| Glue tube |  |  |
| Smeared glue 1 3/4" inside rear of body tube along LL |  |  |
| Aligned engine hook with LL line |  |  |
| Inserted engine mount into body tube until centering ring is even w/ the 5/8" glue mark |  |  |
| Located scrap piece of balsa |  |  |
| Applied glue to centering/body tube joint |  |  |

Signatures                                                                                       Date

Verifier:   ____________________________________           ______________

QA Team: _____________________________________          ______________

Suggestions for improvement (materials or processes): _____________________ _________________________________________________________________

_________________________________________________________________

_________________________________________________________________

_________________________________________________________________

|  | Step Completed |  |
| --- | --- | --- |
| ATTACHING FINS | YES | NO |
| Applied thin layer of glue to edge of fin |  |  |
| Allowed to dry (1 minute for model) |  |  |
| Applied second layer of glue to edge of fin |  |  |
| Attached fin #1 to body tube along one of fin lines flush w/ end |  |  |
| Applied thin layer of glue to edge of fin #2 |  |  |
| Allowed to dry (1 minute for model) |  |  |
| Applied second layer of glue to edge of fin #2 |  |  |
| Attached fin #2 to body tube along one of fin lines flush w/ end |  |  |
| Applied thin layer of glue to edge of fin #3 |  |  |
| Allowed to dry (1 minute for model) |  |  |
| Applied second layer of glue to edge of fin #3 |  |  |
| Attached fin #3 to body tube along one of fin lines flush w/ end |  |  |
| Applied thin layer of glue to edge of fin #4 |  |  |
| Allowed to dry (1 minute for model) |  |  |
| Applied second layer of glue to edge of fin #4 |  |  |
| Attached fin #4 to body tube along one of fin lines flush w/ end |  |  |
| Check fin #1 alignment |  |  |
| Check fin #2 alignment |  |  |
| Check fin #3 alignment |  |  |
| Check fin #4 alignment |  |  |
| Let glue set |  |  |
| Stood rocket on end |  |  |
| Let glue dried completely |  |  |

Signatures                                                                                       Date

Verifier:     ____________________________________           ______________

QA Team: _____________________________________          ______________

Suggestions for improvement (materials or processes): _____________________ _________________________________________________________________

|  | Step Completed |  |
| --- | --- | --- |
| ATTACH SHOCK CORD | YES | NO |
| Cut out shock cord from front page |  |  |
| Attached shock cord to shock cord mount |  |  |
| Applied glue to shock cord mount |  |  |
| Folded edge of shock cord mount over glued shock cord |  |  |
| Applied glue to shock cord mount |  |  |
| Folded over shock cord second time |  |  |
| Held shock cord for 1 minute |  |  |
| Glued shock cord mount 1" inside body tube |  |  |
| Held until glue sets |  |  |
| Let dry completely |  |  |

Signatures                                                                                       Date

Verifier:     ____________________________________           ______________

QA Team: _____________________________________          ______________

Suggestions for improvement (materials or processes): _____________________ _________________________________________________________________

_________________________________________________________________

_________________________________________________________________

_________________________________________________________________

|  | Step Completed |  |
| --- | --- | --- |
| ASSEMBLE NOSE CONE | YES | NO |
| Applied plastic cement to inside rim of nose cone |  |  |
| Pressed nose cone insert into place over plastic cement |  |  |
| inside of nose cone rim |  |  |
| Let dry completely |  |  |
| ASSEMBLE NOSE CONE |  |  |
| Applied plastic cement to inside rim of nose cone |  |  |
| Pressed nose cone insert into place over plastic cement |  |  |
| inside of nose cone rim |  |  |
| Let dry completely |  |  |

Signatures                                                                                       Date

Verifier:      ____________________________________           ______________

QA Team: _____________________________________          ______________

Suggestions for improvement (materials or processes): _____________________ _________________________________________________________________

_________________________________________________________________

_________________________________________________________________

_________________________________________________________________

|  | Step Completed |  |
| --- | --- | --- |
| ATTACH PARACHUTE | YES | NO |
| Passed shroud line on parachute through eyelet |  |  |
| Attached parachute |  |  |
| Passed parachute through loop in shroud |  |  |
| Tied lines |  |  |
| Tied shock cord to nose cone using a double knot |  |  |

Signatures                                                                                       Date

Verifier:     ____________________________________           ______________

QA Team: _____________________________________          ______________

Suggestions for improvement (materials or processes): _____________________ _________________________________________________________________

_________________________________________________________________

_________________________________________________________________

_________________________________________________________________

|  | Step Completed |  |
| --- | --- | --- |
| ATTACH LAUNCH LUG | YES | NO |
| Glued LL centered onto LL line on rocket body |  |  |
| Applied glue fillets along launch lug |  |  |
| Applied glue fillets along fin/body tube joints |  |  |
| Smoothed each fillet with finger |  |  |
| Let glue dry completely |  |  |

Signatures                                                                                       Date

Verifier:     ____________________________________           ______________

QA Team: _____________________________________          ______________

Suggestions for improvement (materials or processes): _____________________ _________________________________________________________________

_________________________________________________________________

_________________________________________________________________

_________________________________________________________________

|  | Step Completed |  |
| --- | --- | --- |
| APPLICATION OF DECALS | YES | NO |
| First decal placed on rocket according to instructions |  |  |
| Bubbles removed from decal |  |  |
| Second decal placed on rocket according to instructions |  |  |
| Bubbles removed from decal |  |  |
| Third decal placed on rocket according to instructions |  |  |
| Bubbles removed from third decal |  |  |
| Fourth decal placed on rocket according to instructions |  |  |
| Bubbles removed from decal |  |  |
| Fifth decal placed on rocket according to instructions |  |  |
| Bubbles removed from decal |  |  |
| Sixth decal placed on rocket according to instructions |  |  |
| Bubbles removed from decal |  |  |
| Seventh decal placed on rocket according to instructions |  |  |
| Bubbles removed from decal |  |  |

Signatures                                                                                       Date

Verifier:   ____________________________________           ______________

QA Team: _____________________________________          ______________

Suggestions for improvement (materials or processes): _____________________ _________________________________________________________________

_________________________________________________________________

|  | Step Completed |  |
| --- | --- | --- |
| PAINTING THE ROCKET | YES | NO |
| Sprayed rocket with white primer |  |  |
| Let dry |  |  |
| Sanded entire rocket |  |  |
| Sprayed completed rocket with white second coat of primer |  |  |
| Let dry |  |  |
| Sprayed nose cone with copper paint |  |  |
| Let dry |  |  |

Signatures                                                                                       Date

Inspector:   ____________________________________           ______________

QA Team: _____________________________________          ______________

Suggestions for improvement (materials or processes): _____________________ _________________________________________________________________

_________________________________________________________________

_________________________________________________________________

_________________________________________________________________

|  | Step Completed |  |
| --- | --- | --- |
| APPLYING CLEAR COAT | YES | NO |
| Applied clear coat to entire rocket |  |  |
| Dry completely |  |  |

Signatures                                                                                       Date

Verifier:     ____________________________________           ______________

QA Team: _____________________________________          ______________

Suggestions for improvement (materials or processes): _____________________ _________________________________________________________________

_________________________________________________________________

_________________________________________________________________

_________________________________________________________________

|  | Step Completed |  |
| --- | --- | --- |
| DISPLAY NOZZLE ASSEMBLY | YES | NO |
| Nozzle #1 painted w/ silver paint |  |  |
| Nozzle #2 painted w/ silver paint |  |  |
| Nozzle #3 painted w/ silver paint |  |  |
| Nozzle #4 painted w/ silver paint |  |  |
| Nozzles allowed to dry |  |  |
| Apply glue to tab on nozzle #1 |  |  |
| Nozzle #1 was placed into hole on base |  |  |
| Apply glue to tab on nozzle #2 |  |  |
| Nozzle #2 was placed into hole on base |  |  |
| Apply glue to tab on nozzle #3 |  |  |
| Nozzle #3 was placed into hole on base |  |  |
| Apply glue to tab on nozzle #4 |  |  |
| Nozzle #4 was placed into hole on base |  |  |

Signatures                                                                                       Date

Verifier:     ____________________________________           ______________

QA Team: _____________________________________          ______________

Suggestions for improvement (materials or processes): _____________________ _________________________________________________________________

_________________________________________________________________

_________________________________________________________________

_________________________________________________________________

|  | Step Completed |  |
| --- | --- | --- |
| ROCKET PREFLIGHT | YES | NO |
| Removed nose cone from rocket |  |  |
| Inserted 4–5 loosely crumpled squares of recovery wadding |  |  |
| Parachute folded accordingly |  |  |
| Parachute lines wrap loosely around rolled parachute |  |  |
| Parachute inserted into body tube of rocket |  |  |
| Shock cord inserted into body tube of rocket |  |  |
| Nose cone inserted onto body tube of rocket |  |  |

Signatures                                                                                       Date

Verifier:     ____________________________________           ______________

QA Team: _____________________________________          ______________

Suggestions for improvement (materials or processes): _____________________ _________________________________________________________________

_________________________________________________________________

_________________________________________________________________

_________________________________________________________________

|  | Step Completed |  |
| --- | --- | --- |
| PREPARE FOR TEST LAUNCH | YES | NO |
| Engine installed |  |  |
| Remove engine |  |  |
| Insert tip to touch propellant |  |  |
| Insert engine into rocket |  |  |
| PREPARE FOR TEST LAUNCH |  |  |
| Engine installed |  |  |

Signatures                                                                                       Date

Verifier:     ____________________________________           ______________

QA Team: _____________________________________          ______________

Suggestions for improvement (materials or processes): _____________________ _________________________________________________________________

_________________________________________________________________

_________________________________________________________________

_________________________________________________________________

Project Deliverables

The checklist will be signed by a verifier and a QA team member. The checklist will also include suggestions by the staff member or subcontracted fitter who did the construction of the rocket deliverable.

## Project Deliverables Test & Acceptance Process

The construction material used for this project has been handpicked by the customer.

## Project Deliverables Acceptance Criteria

All deliverables will be constructed according to kit instructions.

01-Assembling of the Engine Mount:

The engine mount will pass inspection and be accepted if:

- Three marks are on the engine tube at 1/8, ¾, and 1 ½ inches.

- A 1/8th inch slit has been cut 1 ½ inches on the engine tube.

- The assembly hook has been inserted into 1/8th inch slit and glued at the ¾ inch mark.

- The yellow engine block is glued into the front of the mount tube and flush with the end of the mount tube.

- The notched centering ring is glued into place at the 1/8th inch mark.

- The un-notched centering ring is glued flush with the tube end.

- The glue has dried completely.

02-Fin Preparation:

The fin preparation will pass inspection and be accepted if:

- The fins have been carefully cut from the balsa sheet.

- The edges of the fins have been sanded smooth.

03-Marking of Fin and Lug Lines:

The fin and lug line markings will pass inspection and be accepted if:

- The fin and lug lines have been marked on the body tube using the guide.

04-Insertion of Engine Mount:

The engine mount will pass inspection and be accepted if:

- The engine hook and launch lug are aligned.

- The engine mount has been inserted into the body tube and the centering ring is flush with the 5/8th inch mark.

- Extra glue has been added to the 5/8th inch mark inside the body tube.

- The glue has dried completely.

05-Fin Attachment:

The fin attachment will pass inspection and be accepted if:

- The four fins should project straight out from the body tube.

- Each fin should be on the fin lines flush with the end.

- The glue has dried completely.

06-Shock Cord Attachment:

The shock cord attachment will pass inspection and be accepted if:

- The shock cord has been attached one inch to the inside of the body tube.

- The glue has died completely.

07-Nose Cone Assembly:

The nose cone attachment will pass inspection and be accepted if:

- The tube type cement has been used to connect the nose cone and the nose cone insert.

- The glue has died completely.

08-Parachute and Shock Cord Attachment:

The parachute and shock cord attachment will pass inspection and be accepted if:

- The shroud line has been connected through the eyelet on the nose cone insert.

- The parachute has been passed through the parachute line loop.

- The shock cord has been tied to the nose cone with a double knot.

09-Launch Lug Attachment:

The launch lug attachment will pass inspection and be accepted if:

- The launch lug has been centered on the LL line and double glued.

- The glue has dried completely.

10-Paint the Rocket:

The paint job will pass inspection and be accepted if:

- The rocket is painted and the surface is smooth.

11- Decal Application:

The decal application will pass inspection and be accepted if:

- All decals are applied.

- All decals are smooth.

12-Clear Coat Application:

The clear coat application will pass inspection and be accepted if:

- The rocket is smooth.

- The clear coat is completely dry.

13-Display Nozzle Assembly:

The display nozzle assembly will pass inspection and be accepted if:

- The base is painted white.

- The nozzles are painted silver.

- The base plate and the silver nozzles are completely dry.

- The silver nozzles are glued into place on the base plate.

14-Rocket Pre-Flight:

The rocket preflight assembly will pass inspection and be accepted if:

- The rocket will have four or five sheets of recovery wadding loosely packed in the top section.

- The parachute will be folded with the parachute lines loosely wrapped around it.

- The parachute will be placed into the top section of the rocket.

- The cone will be placed onto the top of the rocket.

15-Prepare for Test Launch:

The engine mount will pass inspection and be accepted if:

- The engine will be inserted into the rocket.

Project Audits & Quality Reviews

| Project Quality Audit Review | Planned Date | Quality Review Auditor | Comments |
| --- | --- | --- | --- |
| Assembling of the Engine Mount Audit | Completion of Deliverable | QA Team Member |  |
| Fin Preparation Audit | Completion of Deliverable | QA Team Member |  |
| Marking of Fin and Lug Lines Audit | Completion of Deliverable | QA Team Member |  |
| Insertion of Engine Mount Audit | Completion of Deliverable | QA Team Member |  |
| Fin Attachment Audit | Completion of Deliverable | QA Team Member |  |
| Shock Cord Attachment Audit | Completion of Deliverable | QA Team Member |  |
| Nose Cone Assembly Audit | Completion of Deliverable | QA Team Member |  |
| Parachute and Shock Cord Attachment Audit | Completion of Deliverable | QA Team Member |  |
| Launch Lug Attachment Audit | Completion of Deliverable | QA Team Member |  |
| Paint the Rocket Audit | Completion of Deliverable | QA Team Member |  |
| Decal Application Audit | Completion of Deliverable | QA Team Member |  |
| Clear Coat Application Audit | Completion of Deliverable | QA Team Member |  |
| Display Nozzle Assembly Audit | Completion of Deliverable | QA Team Member |  |
| Rocket Pre-Flight Audit | Completion of Deliverable | QA Team Member |  |

# Quality Plan Approvals

Prepared by:

Project Manager

Approved by:

Project Sponsor

Executive Sponsor

Client Sponsor

5.0 Staffing Management Plan

Project Name: Ansari X Prize Gauchito Rocket

Project Manager: Julie Davis, Space SystemsTechnology Corporation

Project Tracking Number: PMGT 605-0001                   Date:  May 8, 20XX

Project Justification: In developing the 7/8 scaled-down model of the Ansari X Gauchito rocket, the opportunity to address needed modifications identified through quality analysis and testing on the design is invaluable to the Pablo de Leon & Associates space development program. This will also help in the identification, mitigation, and avoidance of risk to the space development program.

Overview of Staff requirements:  
01 -	Fitters (Not generic to the organization)
02 -	Draftsmen
03 -	Painter(s)
04 -	Gluer/Assembler
05 -	Cutter
06 -	Sander Level I		
07 -………………………………………………………………	Sander Level II (5.1.4/13.1.1)
08 -	Engineer

5.1 Key Constraints

Fitters are not generic to the organization; there is a requirement for fitters on this project.

Fitters will be outsourced through a staffing organization and employed based on requirements identified in the WBS and further matched to the histogram.

5.2 Key Assumptions

Resources are properly allocated to ensure load balancing throughout the project.

5.3 Staff Requirements

1. The Gauchito Scaled Demo Project is a project that will utilize much of the expertise within De Leon Enterprises (DLE). This is a precision project that calls upon many skills and skill sets housed under the De Leon logo. As usual, we will rise to the task, asking the best of the best to step forward in anticipation of a well-produced and structurally sound product.

### Below are specific job requirements in support of the Gauchito project; individuals volunteering to support this undertaking will be screened by the project manager, Julie Davis, as it is her responsibility to ensure team success. The primary criteria used in selection will be:

- Attendance and performance

- Special knowledge and skills

- Work history

- Current project workload

- Authorization and cost to work overtime

- Interest in the project

### 5.4 CTU, Staff Acquisition and Team Development

### Selected individuals will be detailed to support this project as an addendum to ongoing requirements. Specific position requirements are listed in the following. A team-building activity will be scheduled after selection and prior to the beginning of the project. This project has an expected completion date of not later than May 10, 20XX.

### Job Description for: STRUCTURAL DRAFTSMAN

This position requires a bachelor’s degree in civil engineering or a closely related field; or five years of experience in rocketry and structural design work including six months of CADD operation and an associate’s degree in civil engineering, drafting, or design technology. This candidate must have experience with ESTES plans. The person assigned to this position will perform other duties as assigned.

### Job Description for: CUTTER

This position requires a bachelor’s degree in knife or scissors use. Selected individual will be able to cut, read, and interpret simple instructions. Individual will be able to cut out, with an appropriate tool, any patterns within one millimeter of specifications. The person assigned to this position will perform other duties as assigned.

### Job Description for: PAINTER I

### 1. Must possess a high school diploma or GED equivalent with three years journey-level experience.

### 2. Will scrape, sandpaper, prime, or seal surfaces prior to painting.

### 3. Must be able to mix, match, and apply paint, varnish, shellac, enamel, and other finishes.

### 4. Will clean and care for brushes, spray guns, and other equipment.
Job Description for: PAINTER II (SUPERVISOR)

### 1. Must possess a high school diploma or GED equivalent with five years master-level experience.

### 2. Responsible for the preparation of all surfaces prior to painting.

### 3. Ensures proper application and adherence to surfaces of all kinds.

### 4. Responsible for checking the condition of woodwork, reporting any carpentry needs, clean-up, and ensuring completeness and customer satisfaction with assigned projects.
Job Description for: TEST ENGINEER (ROCKET SCIENTIST)

### Review test specifications. Develop product test plans and identify and procure test equipment as needed. Interface with local project managers and worldwide customers. Follow NAR guidelines and procedures. Participate in design reviews. Support lab accreditation efforts.

### General requirements: Bachelor’s degree in rocket related engineering required. Master’s degree in engineering preferred. Minimum of 3 years of experience in product.

### Verification testing. Knowledge of rocket specifications and quality systems preferred. Strong computer and communication skills required. Experience with NAR rocket testing methods and equipment experience in electronic hardware and software design methods.

### Job Description for: SANDER I

### 1. Must possess a high school diploma or GED equivalent with three years journey-level experience.

### 2. Uses a machine or hand sands any surface until surface is smooth.
3. Applies filler compound to surfaces to seal wood.

### Job Description for: SANDER II

### 1. Must possess a high school diploma or GED equivalent with five years master-level experience.

### 2. Uses a machine or hand sands to “fine” specifications.

### 3. Responsible for selection of proper “grit” sandpaper and/or sanding appliances.

### 4. Verifies adherence to requirements using applicable tools and/or experience.

### Job Description for: GLUER/ASSEMBLER

### Applies glue between seams in order to bind parts of wooden rockets or other items to make them airtight by either of following methods: (1) guides gluing tool that automatically forces gluing material into seam or (2) fills glue runner (funnel) with glue and guides runner along seam to fill seam with glue. Removes excess glue, using scraper or towel.

5.5 Constraints

### This project has a requirement for fitters that are not organic to DLE. Authorization has been secured from management for external recruitment.

### Job Description for: STRUCTURAL FITTER

This position requires an associate’s degree in fitter sciences or a closely related field; or five years of experience in performing duties including part or equipment location, assembly, and/or construction. Additional requirements for this position include the ability to read and follow simple instructions. The person that fills this position will perform other duties as assigned.

Recruitment

Project Team A will immediately begin recruitment actions through the DLE recruitment section to recruit and hire a qualified candidate(s) to meet these staffing needs. After initial selection by recruitment, candidates will be interviewed by Team A and will need to secure a two-thirds majority vote in order to secure the position(s). This is a process that is now, and will remain, germane to DLE enterprises.
5.6 Continued Employment

Under the general terms of this project and based on the past performance of DLE, this firm anticipates continued contracts in support of this parent project; as such, DLE will support the uninterrupted employment of a minimum of two fitters. Hired individuals will remain under the functional control/management of the assembly section. Reevaluation of this policy will occur not later than one calendar year from the final date of this document.
Sufficient resources are available to support this undertaking. Resource allocation has been formally studied, and supporting documentation (enclosed) is available for review by functional managers. These requirements will be continually evaluated throughout the life of the project and adjustments made as required.

6.0 Communications Management Plan

6.1 Effective communication, internally and externally, is the most overlooked resource in the project management arena. As we delve into yet another project, this will not become a stumbling block for SSTC. We are not reinventing the wheel; we will continue to communicate in a manner that has been proven to work in support of other projects. The following listed procedures have been designed to build communication at all levels and to ease the supporting processes while continuing to capitalize on its inherent benefit.

6.2 The project manager is responsible for disseminating any and all information to concerned parties. This responsibility includes information of the type indicated in the following chart as well as other information deemed pertinent by any interested party. Items not covered in this chart (Enclosure I) will, at a minimum, be posted in the Gauchito project website daily (by close of business).
Note: The project secretary will post weekly status meeting minutes to the company Gauchito project website weekly.
6.3 Information becomes such when it is inclusive of the components who, what, when, where, why, and how; effective communication includes these components and addresses the specific subject of interest. Information communicated about this or any project will be as detailed as possible initially and will be followed up in writing or in an email to all concerned parties. Any input, as a contributor to the successful outcome of this project, will be welcomed.

6.4 When seeking answers or addressing concerns, a response in writing will be provided to the initiating party within 24 hours (work hours). If this time frame is violated or is not sufficient, escalation will follow the below-listed path:
a. Functional department manager
b. Project manager
c. Project sponsor
NOTE: Information will not be communicated directly to the customer except through the personnel listed above. 
Escalation to any of the above-listed parties will be in writing or through email. Additionally, a copy of this correspondence must be maintained by the initiating party.

6.5 The following chart, shown as Enclosure I, is a guide to be used in support of this communications plan; concerned parties have been broken into teams to ensure that information flows are consistent with the needs of both stakeholders and management. This list may not be inclusive, and provisions for the update of it, Enclosure I, or this communications plan are detailed in the paragraph below. 
6.6 Organizational feedback is always welcome. As DLE strives to satisfy the needs of both its customer and employees, concerned individuals should feel free to offer suggestions for improvement, update, or refinement of this or any other policies. Requests for modification of this plan or communication chart(s) will be voiced in writing through the hierarchal structure as specified above. Failure to comply with this minimal communication guidance will result in disciplinary action or termination.

| TEAM A |  |  |
| --- | --- | --- |
| Title | Name | Organization |
| Sponsor | Jeff Tyler | SSTC |
| Project Manager | Julie Davis | SSTC |
| Cost Financing | Gwen Edward | SSTC |
| TEAM B |  |  |
| Title | Name | Organization |
| Quality Assessment | Brian Kirouac | SSTC |
| Quality Assessment | Tom Jones | SSTC |
| TEAM C |  |  |
| Title | Name | Organization |
| Functional Mgr. (Drafting) | B. Jose Alonzo | SSTC |
| Functional Mgr. (Painting) | Robert Muse | SSTC |
| Functional Mgr. (Finishing/Sanding) | Buford T. Linking | SSTC |
| Functional Mgr. (Assembly/Gluer) | J. Christian Bose | SSTC |
| Functional Mgr. (Fitters) | Charles Gooding | SSTC |
| TEAM D |  |  |
| Title | Name | Organization |
| Procurement | Jeanea Brown | SSTC |

Enclosure I

Project Communications Planner

| Who? | What Information? | When? | How? (Form/Medium) |
| --- | --- | --- | --- |
| Team A Team B Team C Team D Project Manager All Recruitment | Supplies confirmation Fitters assignment Change modification request Change mod. confirmation Schedule modification Personnel change (impact) Personnel change (no impact) Facilities (impact) Weather (impact) Weekly status Stage completion Project completion Change mod. confirmation Schedule modification Stage completion Supplies confirmation Supplies requests/mod. Supplies lost or damaged Budgetary changes Change mod. confirmation Schedule modification Personnel change (impact) Personnel change (no impact) Facilities (impact) Weather (impact) Stage completion Project completion Schedule/costs Reports Weekly status meeting minutes Timecards (fitters) | Upon receipt Contract signing Upon receipt Prior to implementation 48 hours prior Prior to change Weekly status meeting Immediate Immediate Weekly Upon completion One-day prior After completion After implementation Upon completion Upon receipt Immediately Immediately Immediately Immediately Immediately Immediately Immediately Immediately Immediately Upon completion One-day prior Weekly Within 24 hours Fridays by 5:00 p.m. | Email/weekly meeting Email/weekly meeting Telephonic Telephonic/email Weekly meeting Telephonic/email Weekly meeting Telephonic/email Telephonic/email Weekly meeting Email/weekly meeting Email Email Email Email Email Email/weekly meeting Email/weekly meeting Email/telephonic Email Email Email Email Email Email Email Email Email/database update Email/project website Fax/email |

7.0 Risk Management Plan

After holding a risk planning meeting, the Gauchito rocket project team focused on all the of the possible project risks and their ramifications and determined that it would be imperative to seek out a risk management plan in order to prepare for risk events and lay out mitigation plans for the risks that seemed the most likely to affect the project’s scope, quality, or schedule.

7.1 Methodology

The Gauchito project team determined that the best way to approach risk determination and

definition would be to bring the entire team together, including all of the individuals of the various skill sets involved in project construction, and brainstorm. It seemed using everyone’s ideas and narrowing the risk events down from there was the most accurate way to determine all of the risks involved from every perspective of this project. Data from previous projects completed by the SSTC team members were used as input to risk definition.

7.2 Roles and Responsibilities

It was decided among the project team that the roles and responsibilities would be laid out as shown in the appendix titled Appendix J, Key or Required Staff. The bulk of the responsibility will be placed on the project manager, as this person has the authority within the team to approve or deny any mitigation plans that are developed as well as the authority to alter the scope statement, the budget, or the quality plan as may be required if any of the determined risk events occurs.

7.3 Budgeting

The Gauchito rocket project team discussed the budget and what effects there would be, if any,

according to each risk event. It was determined that while certain risks could have an effect on the schedule and quality of the project, corrective costs would be negligible unless the risk event went unnoticed and thus uncorrected for an extended time period. Therefore, the project manager, along with the cost and risk managers, determined it would be feasible to allocate roughly 10% of the budget to risk management and mitigation. This percentage will be reevaluated weekly for the life of the project, but it is not necessary to “re-baseline” for this project.

7.4 Timing

After conferring with the rest of the project team, the risk manager, along with the other team managers,

attempted to determine precisely how critically the project schedule might be affected should any of the risk events occur. It was determined that, with the mitigation plans that were approved by the project manager, the schedule would take a minimal hit if any one event occurred. Buffers were already written into the schedule should any unforeseen overtures occur, in order to prevent the project going past its scheduled end date, and the team feels these buffers will be appropriate for the risk management plan; rewriting the project schedule will be unnecessary.

7.5 Risk Categories

It seemed most appropriate, according to the Gauchito rocket project team, to categorize the risks by

the three major constraints of any project. These three constraints are, of course, cost, quality, and schedule. The reasons for selecting these three particular categories are as follows: cost, as any risk event that occurs, will inevitably affect the project’s budget in some form or another; quality, because it often happens that in order to mitigate a risk event or alter a project plan after an unexpected risk occurs that effects cost or schedule, time and money have to be reallocated, and that often alters the quality of a product; and schedule, due to the fact that many risk events on any project alter the schedule in some way or other, be it a large or small change.

7.6 Definition of Risk Probability and Impact

After careful consideration and collaboration among all of the plan managers on the project, it

was determined that a project of this scale needed impact and probably measurements to signify low, moderate, and high. Very low and very high were deemed unnecessary. Numeric values were assigned to each of these levels as follows:

Probability –

| Low / 0.05 | Medium / 0.1 | High / 0.5 |
| --- | --- | --- |

Impact –

| Low / 0.1 | Medium / 0.3 | High / 0.5 |
| --- | --- | --- |

The determined risk events were scored on their probability and impact in a risk assessment table, prior to being placed into the Probability Impact Matrix. The total ratings in the table, which were determined by taking probability multiplied by impact, can be used to determine the organization’s sensitivity to each risk event listed.

| Activity |  | Probability of Risk |  |  | Magnitude of Damage |  |  | Planned Action |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Rank | Low/0.05 | Med./0.1 | High/0.5 | Low/0.1 | Med./ 0.3 | High/0.5 | Total Rating | Type of Action |
| Key personnel unavailable | 3 |  | X |  |  |  | X | 0.05 | Ensure contractors are available if necessary |
| Delayed delivery of materials and equipment | 1 |  | X |  |  |  | X | 0.05 | Make delivery a requirement in supplier contracts |
| Weather | 5 |  | X |  | X |  |  | 0.01 | Change schedule if necessary |
| Materials shortages | 4 | X |  |  |  | X |  | 0.03 | Contract with current supplier and identify alternate suppliers if needed |
| Damage to original parts provided in kit | 2 | X |  |  |  | X |  | 0.03 | Insurance and liability waiver |

Revised Stakeholder Tolerances

After determining the risk categories, the specific risk events, their probability and impact,

and their total ratings, all of this information was put together and brought before the project sponsor for approval before it was presented to the primary stakeholders. The risk events were laid out before the project stakeholders, as well as the mitigation plans that had been approved for each event. After careful consideration and discussions between themselves, the project sponsor, and the project manager, the primary stakeholders informed the project stakeholders that they would tolerate the risk events as they were laid out and were more than willing to allow SSTC to continue with the project. The stakeholder tolerances did not have to be altered in this instance, but as the project is monitored for risks, the stakeholders will be kept abreast of any changes; should their risk tolerance change, it will be documented for this project and for future reference.

7.7 Reporting Formats for Risk Register

The risk register, as shown in the example below, lays out the definition of the risk, what category it

fits into, the root cause of the risk event (if the root cause has been determined and is relevant to the project), the triggers for the risk, and how SSTC will respond to the risk event. There will be weekly quality assessments, and at this time the risk manager will go along with the quality manager, and the RM will be assessing the progress of the project and any occurrences that could be considered a risk. The assessments, as well as any and all reports from the construction staff and/or the functional managers, will all be used to determine risk occurrences, which will all go into the register, be they big or small.

| Risk Register Project Revision: Date: |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Risk # | Risk Description | Risk Root Cause | Risk Category | Trigger | Risk Response |  |
| 1 |  |  |  |  |  |  |
| 2 |  |  |  |  |  |  |
| 3 |  |  |  |  |  |  |
| 4 |  |  |  |  |  |  |

7.8 Tracking

It is imperative that any risk events be tracked throughout the life of this project, be they big or small,  as a small risk is likely to become a big risk and a detriment to the project if it goes unchecked for a length of time. As this information can be important to any member of the project, it needs to be easily accessible; therefore, each plan manager, as well as the project manager, has copies of the risk register and the weekly assessments available for viewing upon request.

8.0 Procurement Management Plan

8.1 Contract Types

There are several different contracts to choose from, so it was left to the procurement manager to determine what contracts would be the most beneficial for the Gauchito rocket project team, in order to ensure that all necessary materials and equipment were delivered in a timely fashion without it becoming a huge expense to the organization. The procurement manager, after discussing all of the materials and equipment to be purchased, determined that the best form of contract to use for materials and equipment (M&E) purchases was firm fixed price.

These contracts were entered into with a clear understanding that all of the M&E purchased was to be delivered no later than a week prior to the project start. This was agreed upon by the organization and the suppliers, and the legal documents were filed with legal, with copies being distributed to the project manager, the project sponsor, and a copy to go on file in the procurement office.

There was also a need to outsource the fitters for this project, as that skill set is no longer available on-staff within the organization. After a discussion with H/R and using the quality manager’s research, it was determined that the fitters would be contracted from the local fitter’s union. This means that contracts will be drawn up specifying their pay per hour, their breaks and lunches, and all other requirements necessary to meet union requirements. Because these fitters are unionized and will have a specific hourly wage for their skill set and experience, it was decided that a fixed-price contract would be best in this instance as well. The fitters will receive their hourly wages and that will be all, as there will not be any overtime or extraneous costs where the outsourced staff is involved.

8.2 Uses of Organizational Procurement, Contracting, or Purchasing Departments

The procurement manager, along with the rest of the procurement department, was responsible for

determining which suppliers to contact, drawing up all of the requests for proposals (RFPs), creating the benchmark to determine the best supplier to meet the project team’s needs, determining what types of contracts to enter into with suppliers, and managing those contracts throughout the life of this project.

8.3 Standardized Procurement Documents

There are several forms of standardized documents used in procurement, many of which were

used for this project. These documents include the firm fixed-price contracts entered into with the suppliers, the requests for proposal sent out to several suppliers, and the benchmark.

8.4 Constraints and Assumptions

There are a number of constraints and assumptions that have to be considered with any project,

and this one is no exception. The assumptions and constraints for this project are as follows:

Constraints:

- There are no available fitters within the organization.

- Trained fitters have to be outsourced for this project.

- Delayed delivery of materials and/or equipment will result in a schedule delay.

Assumptions:

- The materials and equipment will arrive one week prior to project start date.

- All necessary personnel will be available at the time of the project start.

- The contracts will be followed as written without any delays or difficulties.

8.5 Purchase and Acquisition Lead Times

The suppliers for all of the necessary materials and equipment are in the United States and provide

rush delivery, but that is no reason to delay the purchase of the necessary M&E. It was determined that the wisest time to place the purchase orders was 12 days prior to project start to ensure that the suppliers had the necessary materials and equipment in stock and ready to ship in order to ensure it all arrived promptly on the designated delivery date.

8.6 Types of Warranties

It was clearly stated upon the purchase of the materials and equipment necessary for this project

that everything came with a manufacturer warranty, and the stakeholders and project sponsor all deemed these warranties sufficient for this project because this rocket is a test product and will not be used repeatedly, but rather for data gathering.

8.7 Probability and Impact Matrix

| Probability and Impact Matrix |  |  |  |  |
| --- | --- | --- | --- | --- |
| Probability |  |  |  |  |
| 0.5 |  |  |  |  |
| 0.1 |  | Risk 5 |  | Risk 1 Risk 3 |
| 0.01 |  |  | Risk 2 Risk 4 |  |
| Impact |  | 0.1 | 0.3 | 0.5 |
|  | = High-Level Risk—Resolve immediately |  |  |  |  |
|  | = Moderate Risk—Track through the life of the project |  |  |  |  |
|  | = Minimal Risk—Be aware of it, but no tracking necessary |  |  |  |  |

Benchmark

| Benchmark |  |  |  |  |
| --- | --- | --- | --- | --- |
| Suppliers | Ballard Power | Quantum Tech | Cordant Tech | Pratt & Whitney |
| Cost of Hybrid Engines (4) | $12,000 | $10,000 | $10,750 | $11,000 |
| Cost of M&E | $4,500 | $5,000 | $5,000 | $5,500 |
| Delivery Time | 1.5 weeks | 1 week | 2 weeks | 2.5 weeks |
| Delivery Cost | $200 | $125 | $175 | $195 |
| RFP Score | 8 | 10 | 9 | 10 |
| Quantum Tech has the most criteria matching what the Gauchito project team is looking for. |  |  |  |  |
| Therefore, it will be the obvious choice for the supplier for the necessary specialty hybrid engines. |  |  |  |  |

APPENDIX A

Space Systems Technology Corporation

Ansari X Prize Cup-Gauchito Rocket

Project Charter

Project Name: Ansari X Prize Cup Gauchito Rocket

Project Manager: Julie Davis

Project Tracking Number: PMGT 605-0001                                    Date:  May 7, 20XX

Project Justification:

This project will address design consideration of the Gauchito rocket. The rocket’s design, launch, and test results can be observed using a 7/8 scale of the full-sized rocket. This approach provides a valid measurement of the rocket’s success without the time and expense necessary to build a full-sized rocket. This will also help in the identification, mitigation, and avoidance of risk to the Pablo de Leon X Prize entry. This project is being undertaken to show that our company has the ability to produce a reliable test product that accurately duplicates the final full-sized rocket.

Overview of Deliverables:

1.0 ASSEMBLE ENGINE MOUNT

2.0 FIN PREPARATION

3.0 MARK FIN AND LAUNCH LUG LINES

4.0 INSERTING ENGINE MOUNT

5.0 ATTACH FINS

6.0 ATTACH SHOCK CORD

7.0 ASSEMBLE NOSE CONE

8.0 ATTACH PARACHUTE/SHOCK CORD

9.0 ATTACH LAUNCH LUG

10.0 PAINTING THE ROCKET

11.0 APPLICATION OF DECALS

12.0 APPLYING CLEAR COAT

13.0 DISPLAY NOZZLE ASSEMBLY

14.0 ROCKET PREFLIGHT

15.0 PREPARE FOR TEST LAUNCH

Specific Project Objectives and Success Criteria:

A. The project goal is to build a functional model rocket at 7/8 the actual size within three months from the start date of the project.

B. The SSTC project manager “PM” Julie Davis will be responsible for providing the sponsor Jeff Tyler with the scheduling status on a daily to weekly basis as this is a short duration project.

- Cost

      - The Gauchito rocket 7/8 model rocket will be built on the estimated funding of $63,000 dollars.

      - The cost will be further defined as the project resources and cost estimates progress using SSTC existing templates. The budget status shall be provided to the project sponsor on a weekly basis.

- Quality

A. The Gauchito rocket is to be built as a 7/8 scale model of the planned full-size rocket the Delta II.

B. The Gauchito rocket will be built according to all specifications in the kit.

C. Length 39.37 ft, diameter 7.28 ft, GTOW 17,637 lb, DRY WT 5291 lb.

D. All deliverables stated will be inspected by QA staff before completion of rocket.

E. Risk management shall be addressed by the SSTC team in tandem with QA.

F. Testing will be done by the test staff to gather metrics during the test launch.

G. Goal is an altitude of 67 miles with a max speed of 2,684 mph.

Primary Stakeholders and Roles:

The primary stakeholders are as follows.

| Name | Role | Responsibilities/Authority |
| --- | --- | --- |
| SSTC Mr. Jeff Tyler | Pablo de Leon & Associates/Signoff Charter | Fulfill customer contract (e.g. funding; monitor contract fulfillment, coordinating test site and rocket test launch demonstration). Approval of project completion and closure. |
| SSTC Mr. Jeff Tyler | Pablo de Leon & Associates Project Sponsor/Signoff Charter | Communicate with stakeholders and commitment of personnel resources. |
| SSTC Ms. Julie Davis | Pablo De Leon & Associates-Ansari X Prize Gauchito Rocket Project Manager/Signoff Charter/Scope | Responsibilities: Coordinate the project planning, executing, monitoring and controlling, and closing, following DOD’s processes based on the PMI. Ensure project deliverables are completed on time and in budget. Report progress of project to stakeholders to cover critical path schedule, deliverables, and any identified risks updated during weekly status meetings. Coordinate training for outsourced fitters. Coordinate and lead project meetings. Authority: Communicate with DOD contact on any issues. Communicate directly with project sponsor Major T.J. Stone and DOD executives on status and issues. Communicate with resource officer and affected functional managers regarding resource allocation and scheduling. Authorize changes and any corrections to be taken, to include DOD activities. Limitations: The PM will not manage HR activities regarding DOD personnel. |
| SSTC Julie Davis | Scope | -Project Charter—Julie -Project Preliminary Scope—Tom -Product Description—Gwen -WBS—Julie -Constraints—Julie -Assumptions—Julie |
| SSTC Brian Kirouac | Schedule | -Scheduled start dates for WBS tasks -Major milestones and target dates |
| SSTC Tom Jones | Quality | -Provide quality assurance staff for the project to validate each deliverable. |
| SSTC Gwen Edwards | Cost/Financing | -Preparation of cost estimates -Performance measurement baseline |
| SSTC Kevin LaSalle | Staffing | Responsibility Assignment Matrix -Key or required staff |
| SSTC Jeanea Brown | Risk Manager | Identify—Key risks and provide risk management resources to the project to facilitate identifying risks and planning for contingencies. |
| SSTC Kevin LaSalle | Communications | Description of how the communication for the project is going to proceed. |
| SSTC | Procurement | Coordination of resources with resource officer and any functional managers affected. |

Key Constraints:

- SSTC does not currently have the employee resources available during our project start to finish dates for the fitter positions. If the materials are not delivered in the time frame in which the project was based, there will be a change to the project delivery date that we do not have available to us.

- The materials must be delivered the Friday before project start.

- Project must be completed in 3 months time.

- Estimated budget is not to exceed $63,000.

Key Assumptions:

- All materials for the rocket will have been purchased by SSTC and received no later than the Friday before project start. (Recommended engines are as follows: 1/2A3-2T, A3-4T, A10-3T.)

- All activities associated to building the model rocket will follow the National Association of Rocketry (NAR) Safety Code.

- All project management activities will use SSTC’s project tools, templates, and processes, based on PMI standards.

- The project can be completed in 3 months time and within an estimated budget of $63,000.

Signatures—The following people agree that the above information is accurate:

- SSTC project team members:

Ms. Julie Davis            ____________________________________________

Ms. Gwen Edwards      ____________________________________________

Ms. Jeanea Brown        ____________________________________________

Mr. Tom Jones             ____________________________________________

Mr. Kevin LaSalle        ____________________________________________

Mr. Brian Kirouac        ____________________________________________

- Project sponsor and/or authorizing manager(s):

Mr. Jeff Tyler               ____________________________________________

APPENDIX B

Gauchito Rocket Scaled Demonstration

Product Description

Project Name: Ansari X Prize Gauchito Rocket                                    Date:  May 8, 20XX

Project Overview:

Pablo de Leon and Associates is continuing the concept of scaled rocket validation by requesting the construction of a 7/8 scale of the Delta II rocket. The first company that completes construction of a rocket that meets the requirements will win the competition.

Rocket Components and Steps:

The components of the rocket will be built following the steps in the provided construction plan. The steps are below.

01-Assembling of the Engine Mount

02-Fin Preparation

03-Marking of Fin and Lug Lines

04-Insertion of Engine Mount

05-Fin Attachment

06-Shock Cord Attachment

07-Nose Cone Assembly

08-Parachute and Shock Cord Attachment

09-Launch Lug Attachment

10-Paint the Rocket

11-Decal Application

12-Clear Coat Application

13-Display Nozzle Assembly

14-Rocket Pre-Flight

15-Prepare for Rocket Test Launch

Specific Product Specifications:

The Gauchito rocket will be built according to the following specifications:

- 7/8 scale model of the planned full-size rocket the Delta II.

- The rocket will be assembled with materials and equipment in the assembly kit. All rocket components in the construction kit will be assembled as part of the rocket or launch setup.

- Recommended hybrid engines are as follows: 1/2A3-2T, A3-4T, A10-3T to replace the standard engines in the construction kit. The construction company will select the best engine to meet the performance requirements.

- Length = 39.37 ft, Diameter = 7.28 ft, GTOW 17,637 lb, DRY WT 5291 lb.

Performance: The Gauchito rocket performance will be based upon the following.

- Reaching a launch altitude of 67 miles in less than 17 seconds total flying time.

- Total thrust of 52,910 pounds.

- The maximum speed capable of being reached is 2,684 mph, and it will be part of metrics gathered during test. It is not a determination in measuring if the rocket performance is acceptable. It is, however, a factor in obtaining the launch altitude specified. A reduced speed may make the rocket incapable of reaching the required altitude.

- Payload capacity of three crewmembers or 300 kg.

- Crew environment: Nitrogen-oxygen using pressurized suites in a pure oxygen atmosphere.

Quality:

- The Gauchito rocket will be built according to all instructions in the construction plan.

- All activities associated with building the model rocket will follow the National Association of Rocketry (NAR) Safety Code.

Product Assumptions:

- Pablo de Leon & Associates will take possession of the rocket upon completion of assembly following the above steps and meeting the requirements.

APPENDIX C

Preliminary Scope Statement

Gauchito Rocket

Project Name: Ansari X Prize Gauchito Rocket

Project Manager: Julie Davis

Project Tracking Number: PMGT 605-0001                                                   Date: April 19, 20XX

Project Justification: This project will address design consideration of the Gauchito rocket. The rocket’s design, launch, and test results can be observed using a 7/8 scale of the full-sized rocket. This approach provides a valid measurement of the rocket’s success without the time and expense necessary to build a full-sized rocket. This will also help in the identification, mitigation, and avoidance of risk to the space development program. This project is being undertaken to show that our company has the ability to produce a reliable test product that accurately duplicates the final full-sized rocket. To do this, we will deliver the completed 7/8 scale rocket 3 days after the assembly is completed to Peterson AFB test launch site.

I. Overview of Deliverables:

Reference the work breakdown structure (WBS), prepared as a separate document and an example included in Appendix D, for details on each deliverable.

All deliverables will be constructed according to kit instructions.

1.0 ASSEMBLE ENGINE MOUNT

2.0 FIN PREPARATION

3.0 MARK FIN AND LAUNCH LUG LINES

4.0 INSERTING ENGINE MOUNT

5.0 ATTACH FINS

6.0 ATTACH SHOCK CORD

7.0 ASSEMBLE NOSE CONE

8.0 ATTACH PARACHUTE/SHOCK CORD

9.0 ATTACH LAUNCH LUG

10.0 PAINTING THE ROCKET

11.0 APPLICATION OF DECALS

12.0 APPLYING CLEAR COAT

13.0 DISPLAY NOZZLE ASSEMBLY

14.0 ROCKET PREFLIGHT

15.0 PREPARE FOR TEST LAUNCH

II. Specific Project Objectives and Success Criteria:

- The project objective is to develop, build, and test a working model rocket at 7/8 the actual size within two months from the start date of the project.

- The initial milestones are as follows and can be changed utilizing already implemented change management templates as the project progresses toward completion.

- Schedule

  - The project goal is to build a working model within three months from project start.

  - The demonstration rocket testing will be scheduled within one week of completion of the model rocket, at the test launch facility. The test launch will be scheduled with an alternate date in case the wind speed is over 10 miles per hour on the target date because high wind speed may negatively impact the rocket success.

  - The preliminary schedule in Appendix B shows milestones for each deliverable, based on the WBS. The schedule will be further refined during project planning, and milestones may be moved, depending on factors such as concurrent work activities.

  - Each resource assigned to the project will provide weekly status reports to include issues.

  - The project manager will provide schedule status to the project sponsor and the customer on a weekly basis, given the project’s short duration.

- Cost

  - The build of the rocket will be based on an agreed-upon funding of $50,000.

  - The project planning will further refine the preliminary resource and cost estimates provided in Appendix C. This process will use existing templates and procedures. The project manager will provide budget status to the project sponsor and the customer on a weekly basis, given the project’s short duration.

  - Engineering resources assigned to the project will support refining requirements and cost estimates.

- Quality

  - The scaled composite Gauchito rocket will be a 7/8 scale model of the planned full-sized rocket model.

  - The demonstration rocket will be built to the specifications in the kit, including optional steps, such as fin sanding to optimize performance.

  - All fins available in the kit will be installed, per the fin preparation step, to ensure rocket stability.

  - Quality assurance personnel assigned to the project will prepare a quality assurance plan input to the PM to gather necessary approvals.

  - Quality assurance personnel assigned to the project will examine each individual component produced by a deliverable before attaching each component as part of the rocket. QA will also inspect the rocket prior to launch.

  - Configuration management personnel assigned to the project will support the PM in preparation of a configuration management plan and support the definition of activities for defect correction.

  - Configuration management personnel assigned to the project will maintain a list of issues and resolutions.

  - Risk management personnel assigned to the project will support the PM in preparation of a risk management plan to identify risks, level of risk, and contingencies if the risks should occur.

  - Test personnel assigned to the project will support the PM to provide input to the test plan.

  - The rocket will be launched using the purchased four hybrid rocket engines.

  - The rocket body will remain intact through the test launch, without breaking up before reaching the target altitude, and return safely.

III. Scope Management Issues:

The project scope will be maintained by entering all requirements and work activities into existing program tools for tracking requirements (WBS, scope management plan, project charter, etc.). The activities will meet the project objectives and the contract requirements.

1. Defects:

If defects are identified by QA during construction, they will document and provide the data to the PM. The PM and project team will identify options for correcting the defects and present them, along with the most effective option. Any schedule, cost, risk, and performance impacts will be identified. The change control board (CCB) will approve the corrective action and associated impacts.

The finance personnel assigned to the project will work contract changes as needed due to changes to cost and schedule.

Configuration management will maintain a list of defects and resolutions and CCB minutes.

2. Change requests:

If requests for additional materials or changes in construction vary from those provided in the installation kit, they will complete a change request form and provide it to the PM.

(Note: Changes may be requested due to identifying a better installation technique.)

The request, along with cost, schedule, and risk impacts, will be presented to the CCB for evaluation and approval or denial.

If the change request is approved, the PM will update cost and schedule to incorporate the change. Finance personnel assigned to the project will work contract changes as need due to changes to cost and schedule. Engineering, CM, QA, and risk and technical documentation will be updated accordingly. This includes updates to the kit instructions.

If the change request is denied, no changes will be made to the project scope.

Any additional materials needed due to a change request will be procured by Space SystemsTechnology CorporationTechnology Corporation   and provided to the project test site.

Primary Stakeholders and Roles:

| Name | Role | Responsibilities |
| --- | --- | --- |
| SSTC | Customer | Fulfill customer contract (e.g., funding; monitor contract fulfillment, including participation in Configuration Control Board [CCB], coordinating test site and rocket test launch demonstration). |
| Mr. Jeff Tyler | Project Sponsor/Signoff Scope Statement | Communicate with stakeholders and commitment of personnel resources. |
| Ms. Julie Davis | Project Manager/Signoff Scope Statement | Coordinate the project planning, executing, monitoring and controlling, and closing. Responsible for the project budget, cost, and schedule. Provide schedule, define risks, report status, task personnel resources, coordinate any necessary training, and coordinate and lead CCB and project meetings. The PM will provide input to line managers on staff performance but will not manage HR activities. (Reference full responsibilities and authority in the project charter.) |
| Mr. Tom Jones | Quality Assurance (QA) and Signoff Scope Statement | Provide QA resources to the project to validate each deliverable. Participate in CM processes for possible defect correction in deliverables. |
| Mr. Kevin LaSalle | Staffing Manager/Signoff Scope Statement | Provide staffing resources to the project to coordinate support as specified in the statement of work (SOW). |
| Ms. Gwen Edwards | Cost Management/Signoff Scope Statement | Provide financial resources for contract activities and closure. |
| Mr. Brian | Schedule Management Plan/Signoff Scope Statement | Defining severity levels of potential schedule impacts. Identifying who needs to be involved at each level. Determining how changes will be incorporated into the project schedule. Determining how schedule changes will be communicated to key project stakeholders. |
| Ms. Jeanea Brown | Risk Manager/Signoff Scope Statement | Provide risk management resources to the project to facilitate identifying risks and planning for contingencies. |

IV. Key Constraints:

- SSTC does not currently have the employee resources available during our project start to finish dates for the fitter positions. If the materials are not delivered in the time frame in which the project was based on, there will be a change to the project delivery date that we do not have available to us.

- The materials must be delivered the Friday before project start.

- Project must be completed in 3 months time.

- Estimated budget is not to exceed $63,000.

V. Key Assumptions:

- All materials for the rocket will have been purchased by SSTC and received no later than the Friday before project start. (Recommended engines are as follows: 1/2A3-2T, A3-4T, A10-3T.)

- All activities associated with building the model rocket will follow the National Association of Rocketry (NAR) Safety Code.

- All project management activities will use SSTC’s project tools, templates, and processes, based on PMI standards.

- The project can be completed in 3 months time and within an estimated budget of $63,000.

Signatures—The following people agree that the above information is accurate:

- Project team members:

Ms. Julie Davis, Project Manager                                     ________________________________

Ms. Gwen Edwards, Finance         	                              _________________________________

Mr. Brian, Engineering Manager                                     ________________________________

Mr. Kevin LaSalle, Staffing Manager                             _________________________________

Ms. Jeannea Brown, Risk Manager                                 _________________________________

Mr. Tom Jones, Quality Manager                                   _________________________________

- Project sponsor and/or authorizing manager(s):

Mr. Jeff Tyler, Sponsor                                                     ________________________________

APPENDIX D

WORK BREAKDOWN STRUCTURE

1.0 ASSEMBLE ENGINE MOUNT

1.1 Measure, Mark, and Cut Engine Tube

1.1.1 Lay ruler along engine tube

1.1.2 Measure engine from left of engine tube @ 1/8"

1.1.3 Mark left end of engine tube @ 1/8"

1.1.4 Measure engine from left of engine tube @ 3/4"

1.1.5 Mark from left of engine tube @ 3/4"

1.1.6 Measure engine tube from left of engine tube @ 1 1/2"

1.1.7 Mark from left of engine tube @ 1 1/2"

1.2 Cut Engine Tube

1.2.1 Cut Slit of 1/8" @ 1 1/2 inch mark on engine tube

1.3 Glue, Tube, Assemble Hook

1.3.1 Apply thin line of glue completely around engine at 3/4" mark

1.3.2 Position hook per diagram

1.3.3 Insert engine hook into 1/8" slit on engine mount tube

1.4 Assemble Mylar Ring to Tube

1.4.1 Slide mylar ring onto engine mount tube at 3/4" mark

1.4.2 Let dry

1.5 Assemble Yellow Engine Block to Engine Mount Tube

1.5.1 Apply glue inside front of engine mount tube

1.5.2 Insert yellow engine block flush with the right end per diagram

1.5.3 Let dry

1.6 Assemble Centering Rings

1.6.1 Remove centering rings from card with modeling knife

1.6.2 Apply thin line of glue around engine mount tube @ 1/8" mark

1.6.3 Slide notched centering ring onto glued line @ 1/8" mark

1.6.4 Let glue set

1.6.5 Apply thin line of glue to opposite side of notched center ring flush with end of engine mount tube

1.6.6 Slide un-notched centering ring in place over glue flush with end of engine tube mount

1.6.7 Let dry

1.7 Application of Glue Fillets

1.7.1 Apply glue fillets to both sides of centering rings for reinforcement

1.7.2 Let dry

2.0 FIN PREPARATION

2.1 Sand/Cut Fins

2.1.1 Sand laser cut balsa sheet w/ fine sandpaper

2.2 Cutting Out Fins

2.2.1 Cut out fin #1 w/ modeling knife

2.2.2 Cut out fin #2 w/ modeling knife

2.2.3 Cut out fin #3 w/ modeling knife

2.2.4 Cut out fin #4 w/ modeling knife

2.3 Stack and Sand Fins

2.3.1 Stack fins

2.3.2 Sand edges of fins

3.0 MARK FIN AND LAUNCH LUG LINES

3.1 Cut - Tape

3.1.1 Cut out tube marking guide

3.1.2 Tape tube marking guide around body tube

3.1.3 Mark body tube at arrows

3.1.4 Mark launch lug line as LL on body tube

3.2 Remove guide, connect fins and lug lines, extend LL line

3.2.1 Remove tube marking guide from body tube

3.2.2 Connect fins using door frame

3.2.3 Connect launch lug lines using door frame

3.3 Extend Launch Lug Line

3.3.1 Extend launch lug line 3 3/4" from end of tube

4.0 INSERTING ENGINE MOUNT

4.1 Mark inside of tube @ 5/8" where LL is

4.1.1 Measure inside tube to 5/8" position on tube

4.1.2 Mark inside tube at 5/8"

4.2 Glue Tube

4.2.1 Measure inside rear of body tube to 1 3/4" position on tube

4.2.2 Use finger to smear glue 1 3/4" inside rear of body tube along LL

4.3 Assemble Engine Hook

4.3.1 Align engine hook with LL line

4.3.2 Insert engine mount into body tube until centering ring is even w/ the 5/8" glue mark

4.3.3 Let dry

4.4 Gluing Center Body Ring

4.4.1 Locate scrap piece of balsa to apply glue

4.4.2 Apply glue to centering/body tube joint

4.4.3 Let dry

5.0 ATTACH FINS

5.1 Attach Fin #1

5.1.1 Apply thin layer of glue to edge of fin

5.1.2 Allow to dry (1 minute for model)

5.1.3 Apply second layer of glue to edge of fin

5.1.4 Attach fin to body tube along one of fin lines flush w/ end

5.2 Attach Fin #2

5.2.1 Apply thin layer of glue to edge of fin #2

5.2.2 Allow to dry (1 minute for model)

5.2.3 Apply second layer of glue to edge of fin #2

5.2.4 Attach fin #2 to body tube along one of fin lines flush w/ end

5.3 Attach Fin #3

5.3.1 Apply thin layer of glue to edge of fin #3

5.3.2 Allow to dry (1 minute for model)

5.3.3 Apply second layer of glue to edge of fin #3

5.3.4 Attach fin #3 to body tube along one of fin lines flush w/ end

5.4 Attach Fin #4

5.4.1 Apply thin layer of glue to edge of fin #4

5.4.2 Allow to dry (1 minute for model)

5.4.3 Apply second layer of glue to edge of fin #4

5.4.4 Attach fin #4 to body tube along one of fin lines flush w/ end

5.5 Check Fin Alignment

5.5.1 Check fin #1 alignment as shown in diagram

5.5.2 Check fin #2 alignment as shown in diagram

5.5.3 Check fin #3 alignment as shown in diagram

5.5.4 Check fin #4 alignment as shown in diagram

5.6 Allow Glue to Dry

5.6.1 Let glue set

5.6.2 Stand rocket on end

5.6.3 Let glue dry completely

6.0 ATTACH SHOCK CORD

6.1 Cut Out Shock Cord Mount

6.1.1 Cut out shock cord from front page

6.2 First Glue Application

6.2.1 Attach shock cord to shock cord mount

6.2.2 Apply glue to shock cord mount

6.2.3 Fold edge of shock cord mount forward over glued shock cord

6.3 Second Glue Application

6.3.1 Apply glue to shock cord mount

6.3.2 Fold forward again-see diagram for clarification

6.4 Squeeze and Hold

6.4.1 Squeeze shock cord/shock cord mount tightly

6.4.2 Hold for 1 minute

6.5 Attaching Shock Cord Mount

6.5.1 Glue mount 1" inside body tube

6.5.2 Hold until glue sets

6.5.3 Let dry completely

7.0 ASSEMBLE NOSE CONE

7.1 Glue Nose Cone

7.1.1 Apply plastic cement to inside rim of nose cone

7.1.2 Press nose cone insert into place over plastic cement inside of nose cone rim

7.1.3 Let dry completely

8.0 ATTACH PARACHUTE/SHOCK CORD

8.1 Attach Lines

8.1.1 Pass shroud line on parachute through eyelet

8.2 Attach Parachute

8.2.1 Pass parachute through loop in shroud-look to diagram for clarification

8.3 Tie Lines

8.3.1 Tie shock cord to nose cone using a double knot

9.0 ATTACH LAUNCH LUG

9.1 Glue Launch Lines

9.1.1 Glue LL centered onto LL Line on rocket body

9.2 Application of Glue Fillets

9.2.1 Apply glue fillets along launch lug

9.2.2 Apply glue fillets along fin/body tube joints

9.2.3 Smooth each fillet with finger

9.2.4 Let glue dry completely

10.0 PAINTING THE ROCKET

10.1 Apply First Coat

10.1.1 Spray rocket with white primer

10.1.2 Let dry

10.2 Sand

10.2.1 Sand entire rocket

10.3 Apply Final Coat

10.3.1 Spray completed rocket with white second coat of primer

10.3.2 Let dry

10.3.3 Spray nose cone with copper paint

10.3.4 Let dry

11.0 APPLICATION OF DECALS

11.1 Apply First Decal

11.1.1 Remove first decal from back sheet

11.1.2 Place on rocket where indicated

11.1.3 Rub decal to remove bubbles

11.2 Apply Second Decal

11.2.1 Remove second decal from backing sheet

11.2.2 Place on rocket where indicated

11.2.3 Rub decal to remove bubbles

11.3 Apply Third Decal

11.3.1 Remove third decal from backing sheet

11.3.2 Place on rocket where indicated

11.3.3 Rub decal to remove bubbles

11.4 Apply Fourth Decal

11.4.1 Remove fourth decal from backing sheet

11.4.2 Place on rocket where indicated

11.4.3 Rub decal to remove bubbles

11.5 Apply Fifth Decal

11.5.1 Remove fifth decal from backing sheet

11.5.2 Place on rocket where indicated

11.5.3 Rub decal to remove bubbles

11.6 Apply Sixth Decal

11.6.1 Remove sixth decal from backing sheet

11.6.2 Place on rocket where indicated

11.6.3 Rub decal to remove bubbles

11.7 Apply Seventh Decal

11.7.1 Remove seventh decal from backing sheet

11.7.2 Place on rocket where indicated

11.7.3 Rub decal to remove bubbles

12.0 APPLYING CLEAR COAT

12.1 Apply Clear Coat to Entire Rocket

12.1.1 Apply clear coat to entire rocket

12.1.2 Dry completely

13.0 DISPLAY NOZZLE ASSEMBLY

13.1 Spray Nozzle Base White

13.1.1 Paint nozzle #1 w/ silver paint pen

13.1.2 Paint nozzle #2 w/ silver paint pen

13.1.3 Paint nozzle #3 w/ silver paint pen

13.1.4 Paint nozzle #4 w/ silver paint pen

13.1.5 Allow to dry

13.2 Apply Glue

13.2.1 Apply glue to tab on nozzle #1

13.2.2 Place nozzle #1 into hole on base

13.2.3 Apply glue to tab on nozzle #2

13.2.4 Place nozzle #2 into hole on base

13.2.5 Apply glue to tab on nozzle #3

13.2.6 Place nozzle #3 into hole on base

13.2.7 Apply glue to tab on nozzle #4

13.2.8 Place nozzle #4 into hole on base

14.0 ROCKET PREFLIGHT

14.1 Prepare

14.1.1 Remove nose cone from rocket

14.1.2 Locate recovery wadding

14.1.3 Insert 4–5 loosely crumpled squares of recovery wadding

14.2 Spike

14.2.1 Pull parachute into a spike-see diagram for clarification

14.3 Fold

14.3.1 Fold parachute according to diagram

14.4 Roll

14.4.1 Roll parachute according to diagram

14.5 Re-insert

14.5.1 Wrap lines loosely around rolled parachute-see diagram for clarification

14.5.2 Insert parachute into body tube of rocket

14.5.3 Insert shock cord into body tube of rocket

14.5.4 Insert nose cone into body tube of rocket

15.0 PREPARE FOR TEST LAUNCH

15.1 Insert Engine

15.1.1 Remove engine

15.1.2 Insert tip to touch propellant

15.1.3 Insert engine into rocket

APPENDIX E

COST ROLLUP ESTIMATES

(see next page)

# APPENDIX F

# SCHEDULED START DATES

| Name | Duration | Start Date | Finish Date |
| --- | --- | --- | --- |
| 1.0 ASSEMBLE ENGINE MOUNT | 95 | 5/22/20XX | 6/5/20XX |
| -1.1 Measure, Mark, and Cut Engine Tube | 35 | 5/22/20XX | 5/26/20XX |
| -1.2 Cut Engine Tube | 2 | 5/26/20XX | 5/26/20XX |
| -1.3 Glue, Tube, Assemble Hook | 7 | 5/26/20XX | 5/30/20XX |
| -1.4 Assemble Mylar Ring to Tube | 9 | 5/30/20XX | 5/30/20XX |
| -1.5 Assemble Yellow Engine Block to Engine Mount Tube | 10 | 5/31/20XX | 5/31/20XX |
| -1.6 Assemble Centering Rings | 22 | 6/1/20XX | 6/2/20XX |
| -1.7 Application of Glue Fillets | 10 | 6/5/20XX | 6/5/20XX |
| 2.0 FIN PREPARATION | 30 | 5/22/20XX | 5/25/20XX |
| -2.1 Sand/Cut fins | 8 | 5/22/20XX | 5/22/20XX |
| -2.2 Cutting Out Fins | 12 | 5/23/20XX | 5/24/20XX |
| -2.3 Stack and Sand Fins | 10 | 5/24/20XX | 5/25/20XX |
| 3.0 MARK FIN AND LAUNCH LUG LINES | 33 | 5/22/20XX | 5/30/20XX |
| -3.1 Cut - Tape | 13 | 5/22/20XX | 5/25/20XX |
| -3.2 Remove Guide, Connect Fins and Lug Lines, Extend LL Line | 16 | 5/25/20XX | 5/30/20XX |
| -3.3 Extend Launch Lug Line | 4 | 5/30/20XX | 5/30/20XX |
| 4.0 INSERTING ENGINE MOUNT | 43 | 6/6/20XX | 6/9/20XX |
| -4.1 Mark Inside of Tube @ 5/8" Where LL Is | 7 | 6/6/20XX | 6/6/20XX |
| -4.2 Glue Tube | 5 | 6/6/20XX | 6/7/20XX |
| -4.3 Assemble Engine Hook | 18 | 6/7/20XX | 6/8/20XX |
| -4.4 Gluing Center Body Ring | 13 | 6/9/20XX | 6/9/20XX |
| 5.0 ATTACH FINS | 73 | 6/12/20XX | 6/16/20XX |
| -5.1 Attach Fin #1 | 10 | 6/12/20XX | 6/13/20XX |
| -5.2 Attach Fin #2 | 10 | 6/12/20XX | 6/13/20XX |
| -5.3 Attach Fin #3 | 10 | 6/12/20XX | 6/13/20XX |
| -5.4 Attach Fin #4 | 10 | 6/12/20XX | 6/13/20XX |
| -5.5 Check Fin Alignment | 16 | 6/13/20XX | 6/15/20XX |
| -5.6 Allow Glue to Dry | 17 | 6/15/20XX | 6/16/20XX |
| 6.0 ATTACH SHOCK CORD | 44 | 5/22/20XX | 5/26/20XX |
| -6.1 Cut Out Shock Cord Mount | 5 | 5/22/20XX | 5/22/20XX |
| -6.2 First Glue Application | 12 | 5/22/20XX | 5/24/20XX |
| -6.3 Second Glue Application | 8 | 5/24/20XX | 5/25/20XX |
| -6.4 Squeeze and Hold | 6 | 5/25/20XX | 5/25/20XX |
| -6.5 Attaching Shock Cord Mount | 13 | 5/25/20XX | 5/26/20XX |
| 7.0 ASSEMBLE NOSE CONE | 16 | 5/22/20XX | 5/23/20XX |
| -7.1 Glue Nose Cone | 16 | 5/22/20XX | 5/23/20XX |
| 8.0 ATTACH PARACHUTE/SHOCK CORD | 18 | 5/30/20XX | 6/2/20XX |
| -8.1 Attach Lines | 7 | 5/30/20XX | 5/31/20XX |
| -8.2 Attach Parachute | 5 | 5/31/20XX | 6/1/20XX |
| -8.3 Tie Lines | 6 | 6/1/20XX | 6/2/20XX |
| 9.0 ATTACH LAUNCH LUG | 32 | 6/19/20XX | 6/22/20XX |
| -9.1 Glue Launch Lines | 4 | 6/19/20XX | 6/19/20XX |
| -9.2 Application of Glue Fillets | 28 | 6/19/20XX | 6/22/20XX |
| 10.0 PAINTING THE ROCKET | 64 | 6/22/20XX | 6/29/20XX |
| -10.1 Apply First Coat | 16 | 6/22/20XX | 6/23/20XX |
| -10.2 Sand | 8 | 6/23/20XX | 6/23/20XX |
| -10.3 Apply Final Coat | 40 | 6/26/20XX | 6/29/20XX |
| 11.0 APPLICATION OF DECALS | 35 | 6/29/20XX | 7/6/20XX |
| -11.1 Apply First Decal | 5 | 6/29/20XX | 6/29/20XX |
| -11.2 Apply Second Decal | 5 | 6/29/20XX | 6/30/20XX |
| -11.3 Apply Third Decal | 5 | 6/30/20XX | 6/30/20XX |
| -11.4 Apply Fourth Decal | 5 | 6/30/20XX | 7/3/20XX |
| -11.5 Apply Fifth Decal | 5 | 7/3/20XX | 7/5/20XX |
| -11.6 Apply Sixth Decal | 5 | 7/5/20XX | 7/5/20XX |
| -11.7 Apply Seventh Decal | 5 | 7/5/20XX | 7/6/20XX |
| 12.0 APPLYING CLEAR COAT | 16 | 7/6/20XX | 7/7/20XX |
| -12.1 Apply Clear Coat to Entire Rocket | 16 | 7/6/20XX | 7/7/20XX |
| 13.0 DISPLAY NOZZLE ASSEMBLY | 32 | 7/10/20XX | 7/13/20XX |
| -13.1 Spray Nozzle Base White | 18 | 7/10/20XX | 7/11/20XX |
| -13.2 Apply Glue | 14 | 7/12/20XX | 7/13/20XX |
| 14.0 ROCKET PREFLIGHT | 42 | 7/13/20XX | 7/20/20XX |
| -14.1 Prepare | 13 | 7/13/20XX | 7/17/20XX |
| -14.2 Spike | 4 | 7/17/20XX | 7/17/20XX |
| -14.3 Fold | 4 | 7/17/20XX | 7/18/20XX |
| -14.4 Roll | 4 | 7/18/20XX | 7/18/20XX |
| -14.5 Re-Insert | 17 | 7/18/20XX | 7/20/20XX |
| 15.0 PREPARE FOR TEST LAUNCH | 32 | 7/21/20XX | 7/26/20XX |
| -15.1 Insert Engine | 32 | 7/21/20XX | 7/26/20XX |

APPENDIX G

# RESPONSIBILITY ASSIGNMENT MATRIX

|  | Member Teams (Deliverables Owners) |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Deliverable(s) | Stage Name | Team A | Team B | Team C | Team D | Core Team | Alternate |
| 1.0 | Assemble Engine Mount |  |  |  |  | CORE | N/A |
|  | Quality Check |  | Brian Kirouac |  |  |  | DoD Rep. |
| 2.0 | Fin Preparation |  |  |  |  | CORE | N/A |
|  | Quality Check |  | Tom Jones |  |  |  | DoD Rep. |
| 3.0 | Mark Fin & Launch Lug Lines |  |  |  |  | CORE | N/A |
|  | Quality Check |  | Brian Kirouac |  |  |  | DoD Rep. |
| 4.0 | Inserting Engine Mount |  |  |  |  | CORE | N/A |
|  | Quality Check |  | Tom Jones |  |  |  | DoD Rep. |
| 5.0 | Attach Fins |  |  |  |  | CORE | N/A |
|  | Quality Check |  | Brian Kirouac |  |  |  | DoD Rep. |
| 6.0 | Attach Shock Cord |  |  |  |  | CORE | N/A |
|  | Quality Check |  | Tom Jones |  |  |  | DoD Rep. |
| 7.0 | Assemble Nose Cone |  |  | J.C. Bose |  |  | B.T. Linking |
|  | Quality Check |  | Brian Kirouac |  |  |  | DoD Rep. |
| 8.0 | Attach Parachute & Shock Cord Assembly |  |  | J.C. Bose |  |  | B.T. Linking |
|  | Quality Check |  | Tom Jones |  |  |  | DoD Rep. |
| 9.0 | Attach Launch Lug |  |  | J.C. Bose |  |  | B.T. Linking |
|  | Quality Check |  | Brian Kirouac |  |  |  | DoD Rep. |
| 10.00 | Painting the Rocket |  |  | Robert Muse |  |  | J.C. Bose |
| 10.2 | Sand |  |  | B.T. Linking |  |  | J.C. Bose |
| 10.3 | Apply White Primer |  |  | Robert Muse |  |  | J.C. Bose |
| 11.00 | Application of Decals |  |  | J.C. Bose |  |  | B.T. Linking |
|  | Quality Check |  | Brian Kirouac |  |  |  | DoD Rep. |
| 12.00 | Applying Clear Coat |  |  | Robert Muse |  |  | J.C. Bose |
|  | Quality Check |  | Tom Jones |  |  |  | DoD Rep. |
| 13.00 | Display Nozzle Assembly |  |  |  |  | CORE | N/A |
|  | Quality Check |  | Brian Kirouac |  |  |  | DoD Rep. |
| 14.00 | Rocket Pre-Flight |  | Tom Jones |  |  | CORE | N/A |
|  | Quality Check | Team A |  |  |  |  | N/A |
| 15.00 | Prepare for Test Launch | Team A | Brian Kirouac |  |  | CORE | N/A |
|  | Quality Check | Team A | Tom Jones |  |  | CORE | N/A |

APPENDIX H

PERFORMANCE MEASUREMENT BASELINES

# APPENDIX I

# MAJOR MILESTONES

| Name | Finish Date |
| --- | --- |
| 1.0 ASSEMBLE ENGINE MOUNT | 6/5/20XX |
| 2.0 FIN PREPARATION | 5/25/20XX |
| 3.0 MARK FIN AND LAUNCH LUG LINES | 5/30/20XX |
| 4.0 INSERTING ENGINE MOUNT | 6/9/20XX |
| 5.0 ATTACH FINS | 6/16/20XX |
| 6.0 ATTACH SHOCK CORD | 5/26/20XX |
| 7.0 ASSEMBLE NOSE CONE | 5/23/20XX |
| 8.0 ATTACH PARACHUTE/SHOCK CORD | 6/2/20XX |
| 9.0 ATTACH LAUNCH LUG | 6/22/20XX |
| 10.0 PAINTING THE ROCKET | 6/29/20XX |
| 11.0 APPLICATION OF DECALS | 7/6/20XX |
| 12.0 APPLYING CLEAR COAT | 7/7/20XX |
| 13.0 DISPLAY NOZZLE ASSEMBLY | 7/13/20XX |
| 14.0 ROCKET PREFLIGHT | 7/20/20XX |
| 15.0 PREPARE FOR TEST LAUNCH | 7/26/20XX |

APPENDIX J

KEY OR REQUIRED STAFF

| TEAM A |  |  |
| --- | --- | --- |
| Title | Name | Organization |
| Customer |  | Pablo De Leon & Associates |
| Sponsor | Jeff Tyler | Pablo De Leon & Associates |
| Cost Financing | Jeanea Brown | Space SystemsTechnology Corporation |
| Engineer | N/A | Space SystemsTechnology Corporation |
| Project Manager | Julie Davis | Space SystemsTechnology Corporation |
| TEAM B |  |  |
| Title | Name | Organization |
| Quality Assessment | Brian Kirouac | Space SystemsTechnology Corporation |
| Quality Assessment | Tom Jones | Space SystemsTechnology Corporation |
| TEAM C |  |  |
| Title | Name | Organization |
| Functional Mgr. (Drafting) | B. Jose Alonzo | Space SystemsTechnology Corporation |
| Functional Mgr. (Painting) | Robert Muse | Space SystemsTechnology Corporation |
| Functional Mgr. (Finishing/Sanding) | Buford T. Linking | Space SystemsTechnology Corporation |
| Functional Mgr (Cutting) | Ben E. Blades | Space SystemsTechnology Corporation |
| Functional Mgr. (Assembly/Gluer) | J. Christian Bose | Space SystemsTechnology Corporation |
| Functional Mgr. (Fitters/Cutters) | Charles Gooding | Space SystemsTechnology Corporation |
| TEAM D |  |  |
| Title | Name | Organization |
| Procurement | I.B. Buying | Space SystemsTechnology Corporation |

APPENDIX K

KEY RISKS

| Activity |  | Probability of Risk |  |  | Magnitude of Damage |  |  | Planned Action |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Rank | Low/0.05 | Med./0.1 | High/0.5 | Low/0.1 | Med./ 0.3 | High/0.5 | Total Rating | Type of Action |
| Key personnel unavailable | 3 |  | X |  |  |  | X | 0.05 | Insure contractors are available if necessary. |
| Delayed delivery of materials and equipment | 1 |  | X |  |  |  | X | 0.05 | Make delivery a requirement in supplier contracts. |
| Weather | 5 |  | X |  | X |  |  | 0.01 | Change schedule if necessary. |
| Materials shortages | 4 | X |  |  |  | X |  | 0.03 | Contract with current supplier and identify alternate suppliers if needed. |
| Damage to original parts provided in kit | 2 | X |  |  |  | X |  | 0.03 | Insurance & Liability Waiver |

APPENDIX L

CONSTRAINTS

- SSTC does not currently have the employee resources available during our project start to finish dates for the fitter positions. If the materials are not delivered in the time frame on which the project was based, there will be a change to the project delivery date that we do not have available to us. This affects the project human resource management knowledge area.

- The materials must be delivered the Friday before project start. This affects the project procurement management knowledge area.

- Project must be completed in 3 months time. This affects the project time management knowledge area.

- Estimated budget is not to exceed $63,000. This affects the project cost management knowledge area.

APPENDIX M

ASSUMPTIONS

- All materials for the rocket will have been purchased by SSTC and received no later than the Friday before project start. (Recommended engines are as follows: 1/2A3-2T, A3-4T, A10-3T.) This is an external event that must occur for the project to be successful.

- All activities associated to building the model rocket will follow the National Association of Rocketry (NAR) Safety Code. This covers implicit and explicit instructions.

- All project management activities will use SSTC’s project tools, templates, and processes, based on PMI standards. This covers implicit and explicit instructions.

- The project can be completed in 3 months time and within an estimated budget of $63,000. This is covered by explicit and implicit instructions as well as a cost baseline analysis and the WBS and schedule.

APPENDIX N

CONSTRUCTION PLANS

WORKS CITED

Parts of the cost management plan were derived from:

# Tyler, M. (2017). Space systems technology corporation - Cost baseline cumulative s curve. Course Documents. Mohave: Space Systems Technology Corporation.

Parts of the schedule plan were derived from:

- Cox, D. (2000). Schedule management plan for Department of Energy BMIS-FM Project. Retrieved from http://www.mbe.doe.gov/me2-5/i-manage/ENG503-2ScheduleManagementPlan.pdf.

- Piscopo, M. (2017). Free project management templates. Project Management Docs. Retrieved from: http://www.projectmanagementdocs.com/#axzz4oRn405Yf

Parts of the communications plan were derived from:

- Piscopo, M. (2017). Communications management plan. Project Management Docs. Retrieved from: http://www.projectmanagementdocs.com/project-planning-templates/communications-management-plan.html#axzz4oRn405Yf

Appendix CR

- Schwable, K.(2015). Information technology project management, 8th ed.. Cengage Learning. Retrieved from https://www.cengagebrain.com/shop/ProductDisplay?urlRequestType=Base&catalogId=10057&categoryId=&productId=666770&errorViewName=ProductDisplayErrorView&urlLangId=-1&langId=-1&top_category=&parent_category_rn=&storeId=10151