## Slide 1: Project management: Classic mistakes

## Slide 2: Project management: Classic mistakes
People-Related Mistakes
Process-Related Mistakes
Product-Related Mistakes
Technology-Related Mistakes

## Slide 3: People-Related Mistakes
Undermined Motivation
Weak Personnel
Uncontrolled Problem Employees
Heroics
Adding People to a Late Project
Noisy, Crowded Offices
Friction Between Developers And Customers
Unrealistic Expectations
Lack of Stakeholder Buy-In
Lack of User Input
Politics Placed Over Substance
Wishful Thinking

## Slide 4: Process-Related Mistakes
Overly Optimistic Schedules
Insufficient Risk Management
Contractor Failure
Insufficient Planning
Abandonment of Planning Under Pressure
Wasted Time During The Fuzzy Front End
Shortchanged Upstream Activities
Inadequate Design
Shortchanged Quality Assurance
Insufficient Management Controls
Premature of Overly Frequent Convergence
Omitting Necessary Tasks From Estimates
Planning to Catch Up Later
Code-like-hell Programming

## Slide 5: product-Related Mistakes
Requirements Gold-Plating
Feature Creep
Developer Gold-Plating
Push-me, Pull-me Negotiation
Research-oriented Development

## Slide 6: technology-Related Mistakes
Silver-Bullet Syndrome
Overestimated Savings From New Tools or Methods
Switching Tools in the Middle of a Project
Lack of Automated Source-Code Control

## Slide 7: Updated Classic Mistakes
Excessive multi-tasking
Confusing estimates with targets
Unclear project vision
Trusting the map more than the terrain
Assuming global development has little impact
Outsourcing to reduce cost
Letting a team go dark
--- Insufficient Management Controls

## Slide 8: Undermined Motivation
Management shows little personal investment in the project and expects total dedication from team members
  Boss goes on vacation
  Makes sure you can get into the building at all hours so you can work on the project
  Boss brings back souvenirs for all team members
Notes: 1996, McConnell, S., Rapid Development: Taming Wild Software Schedules, Microsoft Press, Chapter 3.
1981, Boehm, B. “An Experiment in Small-Scale Application Software Engineering,” IEEE Transactions on Software Engineering (SE7:5), September, 1981, pp. 482-494.

## Slide 9: Weak Personnel
Individual capabilities of team members
  Skills
  Experience
Relationship as a team
  Skill mix
Personnel selections
Notes: 1996, McConnell, S., Rapid Development: Taming Wild Software Schedules, Microsoft Press, Chapter 3.
1981, Boehm, B. “An Experiment in Small-Scale Application Software Engineering,” IEEE Transactions on Software Engineering (SE7:5), September, 1981, pp. 482-494.
1993, Lakhanpal, B., “Understanding the Factors Influencing the Performance of Software Development Groups: An Exploratory Group-Level Analysis,” Information and Software Technology, (35:8), pp. 468-474.

## Slide 10: Uncontrolled Problem Employees
  Failure to take action to deal with problem employee
    most common complaint of team leaders
  Failure to deal with problem personnel
    can threaten effectiveness
Notes: Larson, C, and LaFasto, F. Teamwork: What Must Go Right, What Can Go Wrong, Sage, Newberry Park, CA, 1989.
Failure to deal with problem personnel (e.g., a prima donna programmer) can threaten development effectiveness. This is a common problem and has been well-understood at least since Gerald Weinberg published Psychology of Computer Programming in 1971. Failure to take action to deal with a problem employee is the most common complaint that team members have about their leaders.

## Slide 11: Heroics
Some project teams emphasize project heroics
Emphasizing heroics usually does more harm than good
May undercut ability to take corrective action
  Do not know action is necessary (poor reporting)
May encourage extreme risk taking
May discourage cooperation among stakeholders
Value of steady/consistent progress
Notes: Some project teams place a high emphasis on project heroics, thinking that the certain kinds of heroics can be beneficial. However, emphasizing heroics in any form usually does more harm than good. Sometimes there is a higher premium placed on a can-do attitudes than on steady and consistent progress and meaningful progress reporting. By elevating can-do attitudes above accurate-and-sometimes-gloomy status reporting, such project managers undercut their ability to take corrective action. They don’t even know they need to take corrective action until the damage has been done. Can-do attitudes can escalate minor setbacks into true disasters. An emphasis on heroics can encourage extreme risk taking and discourage cooperation among the many stakeholders in the software development process.

## Slide 12: Adding People To A Late Project
Takes Productivity away from productive team members
  Bringing up-to-date
  Training
New members not immediately productive
  Learning Curve
  Team dynamics
Notes: Brooks, Mythical Man-Month,

## Slide 13: Noisy, Crowded Offices
60% of developers report work environments
  Not sufficiently quiet
  Not sufficiently private
Prevents concentration and productivity flow
Quiet, private offices tend to increase productivity
Notes: About 60 percent of developers report that their work environments are neither sufficiently quiet nor sufficiently private. For many developers, this can prevent concentration and prevent achieving a state of ‘flow’ that is helpful in achieving high levels of productivity. Workers who occupy quiet, private offices tend to perform significantly better than workers who occupy noisy, crowded work bays or cubicles.

## Slide 14: Friction Between Developers And Customers
Customers feel developers not cooperative
  when developers do not agree with customer schedule
  when developers do not deliver on promises
Developers may believe customer schedules unreasonable
Primary effect is poor communication
Secondary effect includes poorly understood requirements
Notes: Friction between developers and customers can arise in several ways. Customers may feel that developers are not cooperative when they refuse to sign up for the development schedule that the customers want or when they fail to deliver on their promises. Developers may feel that customers are unreasonably insisting on unrealistic schedules or requirements changes after requirements have been baselined. There might simply be personality conflicts between the two groups. The primary effect of this friction is poor communication, and the secondary effects of poor communication include poorly understood requirements, poor user-interface design, and, in the worst case, customers’ refusing to accept the completed product.

## Slide 15: Unrealistic Expectations
“One of the most common causes of friction between developers
and their customers or managers is unrealistic expectations.
Often customers simply start with unrealistic expectations (which
is probably just human nature). Sometimes project managers or
developers ask for trouble by getting project approval based on
optimistic estimates. A Standish Group survey listed realistic
expectations as one of the top five factors needed to ensure the
success of an in-house business-software project.”
Sources of “Unrealistic Expectations”
Upper Management 69%
Sales & Marketing 51%
Customers 46%
Project / Program Managers 37%
Development Team 15%

## Slide 16: Lack Of Effective Project Sponsorship
Top management support
  Realistic estimates
  Adequate resource allocation
  Achievable schedules
  Clearing roadblocks
Notes: High-level project sponsorship is necessary to support many aspects of effective development including realistic estimates, adequate resource allocation, and achievable schedules, as well as helping to clear roadblocks once the project is underway. Without an effective project sponsor, other high-level personnel in your organization can force you to accept unrealistic deadlines or make changes that undermine your project.

## Slide 17: Lack Of Stakeholder Buy-In
Stakeholder buy-in
  Executive sponsor
  Team leader
  Team members
  Marketing
  End-users
  Customers
Anyone who has an interest in the project
Notes: All of the major players in a software-development effort must buy in to the project. That includes the executive sponsor, team leader, team members, marketing, end-users, customers, and anyone else who has a stake in it. The close cooperation that occurs only when you have complete buy-in from all stakeholders allows for precise coordination of a software development effort that is impossible to attain without good buy-in.

## Slide 18: Lack Of User Involvement
User involvement is necessary for defining meaningful requirements
The degree of user involvement can affect how quickly or how slowly issues get resolved

## Slide 19: Politics Placed Over Substance
Political Orientations
  Politicians
    Concentrate on relationships with their managers
  Researchers
    Concentrate on searching and gathering information
  Isolationist
    Keep to themselves
  Generalist
    Little bit of all the above
Notes: Larry Constantine (???) reported on four teams that had four different kinds of political orientations. “Politicians” specialized in “managing up”— concentrating on relationships with their managers. “Researchers” concentrated on scouting out and gathering information. “Isolationists” kept to themselves, creating project boundaries that they kept closed to non-team members. “Generalists” did a little bit of everything: they tended their relationships with their managers, performed research and scouting activities, and coordinated with other teams through the course of their normal workflow. Constantine reported that initially the political and generalist teams were both well regarded by top management. But after a year and a half, the political team was ranked dead last. Putting politics over results is fatal to software development effectiveness.

## Slide 20: Wishful Thinking
Hoping something works
  Without logical basis
May lead to schedule issues
  Undermines meaningful planning
Notes: Wishful thinking isn’t just optimism. It’s closing your eyes and hoping something works when you have no reasonable basis for thinking it will. Wishful thinking at the beginning of a project leads to big blowups at the end of a project. It undermines meaningful planning and can be at the root other problems.

## Slide 21: Overly Optimistic Schedules
Under scopes the project
Undermines effective planning
Added pressure on developers
Notes: The challenges faced by someone building a three-month application are quite different than the challenges faced by someone building a one year application. Setting an overly optimistic schedule sets a project up for failure by under scoping the project, undermining effective planning, and abbreviating critical upstream development activities such as requirements analysis and design. It also puts excessive pressure on developers, which hurts developer morale and productivity.

## Slide 22: Insufficient Risk Management
Not doing risk management at all
Identification of risks
Managing / Mitigating Risks
Notes: Some mistakes have been made often enough to be considered classic mistakes. Other potential problems need to be identified project-by-project through risk management. The most common problem with risk management is not doing any risk management at all. The second most common problem with risk management is not doing enough risk management.

## Slide 23: Subcontractor Failure
Subcontracting when “rushed”
Problems with delivery
  Quality
    Requirements
    Interfaces
  Timeliness
Notes: Companies sometimes subcontract pieces of a project when they are too rushed to do the work in-house. (“Subcontractor” can refer either to an individual or to an outsourcing firm.) But subcontractors frequently deliver work that’s late, that’s of unacceptably low quality, or that fails to meet specifications. Risks such as unstable requirements or ill-defined interfaces can be magnified when you bring a subcontractor into the picture. If the subcontractor relationship isn’t managed carefully, the use of subcontractors can undermine a project’s goals. (Note: This question deals specifically with subcontracting part of a project—other items focus on outsourcing full projects.)

## Slide 24: Insufficient Planning
Planning can be done well, and planning can be done poorly. But some projects suffer from simply not doing enough planning at all, i.e., not prioritizing planning as an important activity.

## Slide 25: Abandonment Of Planning Under Pressure
Schedule slippage
Need to update plan
  Avoiding code-and-fix mode
Notes: Projects make plans and then routinely abandon them when they run into schedule trouble. This would not be a problem if the plans were updated to account for the schedule difficulties. The problem arises when the plans are abandoned with no substitute, which tends to make the project slide into code-and-fix mode.

## Slide 26: Wasted Time During The Fuzzy Front End
The “fuzzy front end” is the time before the project starts, the time normally spent in the approval and budgeting process. It’s not uncommon for a project to spend months or years in the fuzzy front end and then to come out of the gates with an aggressive schedule.

## Slide 27: Shortchanged Upstream Activities
“Jumping into coding”
Abandoning
  Requirements
  Architecture
  Design
Notes: Projects sometimes cut out non-coding activities such as requirements, architecture, and design. Also known as “jumping into coding,” the results of this mistake are predictable. Projects that skimp on upstream activities typically have to do the same work downstream at anywhere from 10 to 100 times (???) the cost of doing it earlier.

## Slide 28: Inadequate Design
Special case of “Shortchanging upstream activities”
Not allocating enough time for design
  Possibly results in multiple design cycles
Notes: A special case of shortchanging upstream activities is inadequate design. Rush projects undermine design by not allocating enough time for it and by creating a pressure-cooker environment that makes thoughtful consideration of design alternatives difficult. This results in going through several time-consuming design cycles before the system an be completed.

## Slide 29: Shortchanged Quality Assurance
Victim of schedule slippage
Hurried project that eliminate:
  Design and Code Reviews
  Test Planning
  Minimal Testing
Notes: Projects that are in a hurry often cut corners by eliminating design and code reviews, eliminating test planning, and performing only perfunctory testing. It is common for design reviews and code reviews to be given short shrift in order to achieve a perceived schedule advantage. This often results in the project reaching its feature-complete milestone but then still being too buggy to release.

## Slide 30: Insufficient Management Controls***
Few management controls to provide warnings of schedule slips
Controls originally in place are abandoned once project is in trouble
*** Note: Excluded in 2008 Classic Mistakes

## Slide 31: Premature Or Too Frequent Convergence
Forcing convergence too early
  Unstable release
  Can prolong schedule
Push to prepare for software release
  Improving product performance
  Creating final documentation
  Remove functionality not ready for initial release
  Perform end-to-end testing
Notes: Shortly before a public software release there is a push to prepare the software for release—improve the product’s performance, create final documentation, stub out functionality that’s not going to be ready for the release, perform end-to-end testing including tests that can’t be automated, test the setup program, and so on. On rush projects, there is a tendency to force convergence too early. If the software isn’t close enough to a releasable state, the attempted convergence will fail, and the team will need to attempt to converge again later in the project. The extra convergence attempts waste time and prolong the schedule.

## Slide 32: Omitting Necessary Tasks From Estimates
Poor planning?
Forgetting less visible tasks
Notes: If people don’t keep careful records of previous projects, they forget about the less visible tasks, but those tasks add up. Forgotten activities can add 20 to 30 percent (???) to a development schedule.

## Slide 33: Planning To Catch Up Later
Projects that get behind schedule – stay behind schedule
Importance of “earned value” planning
Notes: If you’re working on a project and it takes you four weeks to meet your first two-week milestone, what’s your status? You’re know that you’re behind schedule, but will you stay behind schedule, or will you catch up later? Project planners commonly plan to catch up later, but they rarely do. Most projects that get behind schedule stay behind schedule.

## Slide 34: Code-like-hell Programming
Synonym for “Code-and-fix” paradigm
Coincides with ambitious schedule
Notes: Some organizations think that fast, loose, all-as-you-go coding is a route to rapid development. If the developers are sufficiently motivated, they reason, they can overcome any obstacles. This is far from the truth. The entrepreneurial model is often a cover for the old code-and-fix paradigm combined with an ambitious schedule, and that combination almost never works.

## Slide 35: Requirements Gold-Plating
Added requirements by developers and/or users
  No clear justification of business need
Users who want best possible system
Developers who want complex capabilities
Notes: Requirements gold plating is the addition of requirements or the expansion of requirements without a clear business justification. Requirements gold plating can be done by end users who want the “system to end all systems” or it can be done by developers who are sometimes more interested in complex capabilities than real users are.

## Slide 36: Feature Creep
The average project experiences about a 25-percent change in requirements over its lifetime. Such a change produces at least a 25-percent addition to the software effort and schedule, which is often unaccounted for in the project’s plans and unacknowledged in the project’s status reports.

## Slide 37: Developer Gold-Plating
Developers fascinated by new technology
Creating “own” implementation of features
  Additional effort needed to:
    Design
    Implement
    Test
    Document
    Support
Notes: Developers are fascinated by new technology and are sometimes anxious to try out new capabilities of their language or environment or to create their own implementation of a slick feature they saw in another product— whether or not it’s required in their product. The effort required to design, implement, test, document, and support features that are not required adds cost and lengthens the schedule.

## Slide 38: Push-me, Pull-me Negotiation
Project Manager approval of schedule slippage while simultaneously adding new tasks
Project Manager aware of scheduling problem
Project Manager adds tasks to alter schedule
Notes: One bizarre negotiating ploy occurs when a manager approves a schedule slip on a project that’s progressing slower than expected and then adds completely new tasks after the schedule change. The underlying reason for this is hard to fathom because the manager who approves the schedule slip is implicitly acknowledging that the schedule was in error. But once the schedule has been corrected, the same person takes explicit action to make it wrong again.

## Slide 39: Research-Oriented Development
Advancing state of the art
Conflicts with
  Tight budget
  Short schedule
Notes: Some projects have goals that push the state of the art—algorithms, speed, memory usage, and so on. That’s fine, but when those projects also have ambitious cost or schedule goals, the combination of advancing the state of the art with a tight budget on a short schedule isn’t achievable.

## Slide 40: Silver-Bullet Syndrome
Over reliance on new technology
  Unused technology – tools
  New methodology
Notes: On some projects, there is an over reliance on the advertised benefits of previously unused technologies, tools, or 3rd party applications and too little information about how well they would do in the current development environment. When project teams latch onto a single new methodology or new technology and expect it to solve their cost, schedule, or quality problems, they are inevitably disappointed.

## Slide 41: Overestimated Savings From New Tools Or Methods
Expecting new technology – tools – methods to reduce cost and/or shorten schedules
Learning curve
Notes: Organizations often assume that first-time usage of a new tool or method will reduce costs and shorten schedules. In reality, first-time use of a new tool or method tends to be subject to a learning curve, and the safest planning assumption is to assume a short-term increase in cost and schedule before the benefits of the new tool or method kick in.

## Slide 42: Switching Tools In The Middle Of A Project
New tool versus newer release
Learning Curve
Notes: This is an old standby that hardly ever works. Sometimes it can make sense to upgrade incrementally within the same product line, from version 3 to version 3.1 or sometimes even to version 4. But the learning curve, rework, and inevitable mistakes made with a totally new tool usually cancel out any benefit when you’re in the middle of a project.

## Slide 43: Lack Of Automated Source-Code Control
Source control tools
  Coordinate working on software
  Backing up versions of software
  Using correct versions of software
Notes: Failure to use automated source-code control exposes projects to needless risks. Without it, if two developers are working on the same part of the program, they have to coordinate their work manually and risk accidentally overwriting someone else’s work. People develop new code to out-of-date interfaces and then have to redesign their code when they discover that they were using the wrong version of the interface. Users report defects that you can’t reproduce because you have no way to recreate the build they were using.

## Slide 44: Excessive Multi-tasking
Working on tasks simultaneously
Switching costs
Notes: When software developers are assigned to more than one project, they must ‘task switch’ as they change their focus from one project to another. They must get out of ‘flow’ on one project and into ‘flow’ on another. Task switching can be a significant factor—some studies (???) have said that each task switch in software development can incur a 5-30 minute downtime as a developer works out of flow on one project and works into flow on the other.

## Slide 45: Confusing Estimates With Targets
Estimates versus Targets
Estimates based on desired results
Notes: Some organizations set schedules based purely on the desirability of business targets without also creating analytically-derived cost or schedule estimates. While target setting is not bad in and of itself, some organizations actually refer to the target as the ‘estimate,’ which lends it an unwarranted and misleading authenticity as a foundation for creating plans, schedules, and commitments.

## Slide 46: Unclear Project Vision
Aligning project goals with organizational goals
Mission Statements
  Goals
  Vision
Notes: The lack of clearly defined and communicated vision undermines the organization’s ability to make and execute project-level plans that are consistent with organization-level goals. Without a clear understanding of the vision, people draw their own conclusions about the purpose of the project and how it relates to their day-to-day work, and they make decisions that run counter to the project’s business objectives. The unclear vision contributes to changes in project direction, including detailed requirements; detailed plans that are misaligned with project priorities; and, ultimately, inability to meet schedule commitments.

## Slide 47: Trusting The Map More Than The Terrain
Ignoring Experience
Reality versus the Plan
Notes: Project teams sometimes invest more confidence in the plans they create than in the experience their project is giving them. Sometimes they will trust the delivery date written on a plan more than the delivery date implied by the project’s track record. If the project reality and the project plans disagree, the project’s reality is correct, and the plans must be wrong. The longer a project team trusts the plans rather than the project reality—i.e., trusts the map more than the terrain—the more difficulty they will have adapting their course successfully.

## Slide 48: Assuming Global Development Has Little Impact
Time Zones
Company Cultures
National Cultures
Single site to Multiple site development
Notes: Multi-site development increases communication and coordination effort between sites. The greater the differences among the sites in terms of time zones, company cultures, and national cultures, the more the total project effort will increase. Some companies naively assume that changing from single-site development to multi-site development will have a negligible impact on effort, but studies have shown that international development will typically increase effort by about 40% compared to single-site development.

## Slide 49: Outsourcing To Reduce Cost
Valid reasons to outsource
  Lack of internal expertise
  Diversifying labor force
  Freeing up in-house staff
  Surge Capacity
  Around the clock development
Notes: Valid reasons to outsource include accessing capabilities that you don’t have in house, diversifying your labor force, freeing up your in-house staff to focus on mission-critical or core-competency projects, adding “surge capacity” to your development staff, and supporting around-the clock development. Many organizations that have outsourced for these reasons have accomplished their objectives. However, some organizations outsource primarily to reduce development costs, and historically those initiatives have not succeeded. Usually outsourcing motivated by cost savings results in higher costs and longer schedules.

## Slide 50: Letting A Team Go Dark
Managing with little oversight
Visibility of team’s progress (lack of)
Notes: On some projects, management allows a team to work with little oversight and little visibility into the team’s progress. This is known as “letting a team go dark.” This practice restricts visibility into project status, and the project doesn’t receive timely warnings of impending schedule slips. Before you can keep a project on track, you have to be able to tell whether it’s on track, and letting a team go dark prevents that.

## Slide 51: Summary: Worst Classic Mistakes
Rank | Classic Mistake | “Often” & “Almost Always” | “Catastrophic” & “Severe”
1 | Unrealistic expectations | 73% | 83%
2 | Overly optimistic schedules | 77% | 78%
3 | Shortchanged quality assurance | 70% | 72%
4 | Wishful thinking | 68% | 76%
5 | Confusing estimates w/ targets | 65% | 71%
6 | Excessive multi-tasking | 71% | 71%
7 | Feature creep | 69% | 61%
8 | Noisy, crowded offices | 69% | 51%
9 | Abandoning planning u/ pressure | 59% | 67%
10 | Insufficient risk management | 68% | 60%
Notes: The risk management field’s concept of risk exposure helps to prioritize the Classic Mistakes based on this survey data. In risk management, Risk Exposure, also known as RE, is calculated by multiplying the likelihood of a risk by its severity. Statistically speaking, the result is the Expected Value of the risk. Sorting risks by their Risk Exposure provides a rough prioritization of the risks.
We applied a similar concept to the results of this Classic Mistakes survey to assess which Classic Mistakes are most problematic overall. We multiplied the approximate average frequency of each Classic Mistake times its average severity to arrive at a Mistake Exposure Index (MEI). This index ranges from 0 to 10, with 0 being the lowest exposure and 10 being the highest. Of the Classic Mistakes covered by this survey, the actual range was 2.6 to 9.9.