# 1-Project Description

The United States Air Force is the aerial and space warfare service branch of the United States Armed Forces (East Coast). During an audit, the USAF concluded that their IT systems were out of date, and that there were many drawbacks to this from an operational and Information Security perspective. They have decided to step up and use a small portion of the government’s budget to upgrade their IT systems at one of the base’s facility. This upgrade includes the replacement of hardware and the implementation of stronger security and STIG software. The USAF has decided to entrust a third party organization to perform these upgrades. Unisys, a worldwide information technology organization has signed a contract in agreement with the scope of the project and has promised to deliver a solution that will exceed the needs of the Air Force.

## Project Details

### Industry:

- Military, Government, Information Technology

### Project Type:

- Information Technology

- Cybersecurity

- Engineering

- Management

### Size of the project:

- Air Force facility size: There are a total of 50 endpoints and 4 physical servers.

- Budget: $200,000

- Duration: 6 months

### Project Structure:

This project’s structure is projectized as the Project Manager and Endpoint lead have full authority to assign priorities, apply resources, and direct the work of persons assigned to the project (Kautilya).

### Location Information:

- USAF Base Location : Tampa Florida

- Base Name: MacDill Air Force Base

- Address: 9211 Marina Bay Dr, Tampa, FL 33621

- Facility Name: 6th Medical Group

- Facility Address: 3250 Zemke Ave, Tampa, FL 33621

### Company Size:

- Unisys has selected 4 employees to work on this project. The team is composed by a Project Manager, an Endpoint Lead, an IT specialist and an Information Security Analysts.

### Involvement in the project:

My title in the project is Cybersecurity analyst, however, I wear many hats. I will be part of the team responsible for planning and meeting deliverables, as well as implementing the new systems and security solutions. My main role however is making sure that the security solutions are implemented and exceeding the Air Force expectations in comparison to what the Air Force currently has.

## Project Scope:

Unisys has promised to replace all of the endpoint computers with new Dell laptops. Since the Air Force’s systems are currently running Windows 7, the OS will be upgraded to Windows 10 using the AF image format which contains very secure group policies. The current Air Force endpoint security stack (HBSS) will be replaced by more efficient security solutions, including Bromium, Carbon Black, and Steel Cloud for STIGs. Unisys has also promised to migrate the current servers at the facility as well as the newly implemented ones on the cloud as this provides more flexibility and scalability. Unisys has decided to use Nutanix as a third party cloud solution in which all the servers can be hosted, managed, and backed up.

# 2-Knowledge Areas (1-10)

## Knowledge Area 1: Project Integration Management

- In June of 2019 I was hired to work at Unisys as a key member of the contract with the Air Force. I was hired as a Cybersecurity analyst to assist with the implementation and maintenance of the security solutions that will replace what is currently in place. As I joined the team, the project had already started, therefore, there already were other team members in the team. The team was already composed by a Project Manager and an Endpoint Lead, as well as the IT specialist. Most of the planning was already done by the Project Manager with some help from the Endpoint lead, which helped lead the operations and some of the initial architecture planning to completion. The Project Manager, together with the team are responsible for the successful completion of the project as specified in the plan.

- Approval was received from the Base to begin implementing our solution. We have already shipped out the Nutanix box and Air Force IT specialists have mounted it in a server rack in the server room. Connection to the Nutanix box includes a 1GB/s switch on a segregated Vlan for the production environment. The switch being used is one that had already been purchased, therefore, we decided to use it for this project. After purchasing the 1GB/s switch we come to find out that the Nutanix box can transfer data at speeds up to 10GB/s which means that even though 1GB/s is good enough and supported, the Air Force could benefit from faster data transfer rates. At this point it is up to management whether we are going to use the 1GB/s switch or the faster one or not. Taking into consideration that purchasing a 10GB/s switch would slow the project down management decided to budget for a new switch. The switched arrived a week later, and as a result the project’s length increased. The purchase of the faster switch also forced the project’s budget to go higher than expected.

- Although this is a small change to the project, there are ways in which this drawback could have been avoided. The most logical way would have been by doing the necessary research on the Nutanix solution, as well as the switch compatibility. The Project Manager was responsible for understanding the features from internal to external as well as for establishing communication with the vendor in every aspect of the solution. The Project Manager could have also requested documentation about the Nutanix solution and shared it among the team for each one of us to take a look and share our opinions. Although we did have several meetings about the solution, the topic about network connectivity between the Nutanix box and the internet at the base was never brought up.

## Knowledge Area 2: Project Scope Management

- In order to accomplish the project’s goal, a scope has been set that specifies the order in which each task will take place. The takes will take place in the following order:

- Making additions to the team as needed before or during the implementation phase.

- Once the team is complete, decide who will be deployed to do the Nutanix installations at the base.

- Before deploying into production, we will stand up a Lab and test our security tools before. This will guarantee that when deployed, the solutions will exceed the Air Force’s expectations.

- Then, the team will be deployed and the Nutanix installation will be completed.

- Once the Nutanix solution is in place and connectivity to it has been tested, the security team will fire up the servers for the security solutions ( Bromium, Carbon Black, Steel Cloud)

- Security policies will then be applied to these servers following best security practices. This way, once the users receive their new system all they need to do is plug and play. The way that the server communicates with the endpoint is via an agent. Both Carbon Black and Bromium require an agent to be installed in the endpoints in order to communicate with their respective management consoles. Steel Cloud does not require an agent, however, but it requires that the systems be in the same network segments in order to provision STIGs changes.

- Once the servers are up and running the users at the 6th medical group will be provided with fully functional laptops that will be managed by the security solutions in place.

- The final phase is to offer administration and management of the security solutions to the Air Force Base indefinitely.

During the last phase, the Air Force will get a good taste of the new systems and security solutions in place and will decide whether to expand the solution to the rest of the facilities on the base and later on to the other bases.

- As the project scope came into place, there were some items that the Project Manager didn’t think about. First, users are not used to these new systems and it will take some time for them to become familiar with the way in which the new security solution operates. Some of the effects that the new security solution may have on the users is the fact that they will no longer be able to download software online unless it is first approved. Users will not be able to insert USB drives other than Government approved. These are some of the challenges that users will experience at the base once the new systems are in place. Because of this last minute user impact, the project will have to get extended and a new section of the plan will need to be added to address the user training on the new platform and creating a policy that the users will abide by.

- The Project Manager could have avoided this drawback by not only focusing on the technical aspect of project planning, but also thinking about the impact this new systems would have on the customer. The majority of an IT Project’s success comes from establishing communications with the stakeholders. Should the project manager have foreseen these difficulties the user training and policy implementation would have made part of the scope during the planning phase.

## Knowledge Area 3: Project Time Management

- Time management has been a priority ever since the project started. Getting the Unisys team and the Air Force personnel together to discuss project plan time-frames and timelines have not been an easy task as everyone is busy with their own schedule. However, there are always successful ways of making cross communication happen. As everyone’s time is limited, the project manager setup weekly meetings and some other meetings that would only occur once a week about different topics in regards to the Air Force needs. Being able to schedule the meetings and get every party who needs to be present to provide information is a difficult task, but it was possible due to excellent time management and planning. During the planning phase, timelines were also established to define the length and time frame of each task and deliverable.

- Unfortunately, due to the drawbacks presented in the project so far, the timeliness and completion of the project have already been pushed for a later date. What seemed to be accomplishable in 6 months has now been pushed to 6 months and a half. Which not only affects the project’s budget, but also fails to meet the deadlines. As expected failure to meet deadlines doesn’t look very good in the eyes of the client.

- To prevent the project’s completion date from extending, the project manager should have done his due diligence and prevented sudden barriers that do nothing but slow down the project’s progress. PM could have foreseen little mistakes such as the explained above by documenting on the project plan every area of the project’s scope before entering the implementation phase.

## Knowledge Area 4: Project Cost Management

- The Government set a budget aside of $150,000 to accomplish the goals of the project. With this said, nothing tremendously challenging has happened to where the project will go over budget yet. However, if small mistakes are continually made, this may change. It is critical that the project plan be established and followed in order to stay within budget. It is also critical that the Project Manager understands the risks that may come during or after the implementation of the new systems. As established in the project plan, the $50,000 will be used to purchase the Laptops for each of the 50 employees at the 6th Medical Group, purchase the Nutanix box, to pay for any shipment of these equipment, and to cover for any third party vendor support pricing as well as the software licenses of the new security solutions and the new operating system ( Win 10)

- A change that impacted the cost of the project is (1) the purchase of a new switch and (2) the time that will need to be spent by training Air Force personnel on the new systems. Time in this case turns into money. Impacted in this context doesn’t mean that the project will go over budget, but that because of planning issues it will cost more than planned.

- Some of the actions that the PM can take to prevent project over-budgeting include the establishment of cost controls by setting up clear cost controls, maintaining record of expenses, and last but not least, updating the changes that take place that affect cost.

## Knowledge Area 5: Project Quality Management

- In order to deliver the best quality services to the Air Force, the Project Manager integrated into the plan the need for identifying the quality requirements and standards for the project. Only when these have been identified can the expectations be met and/or exceeded when delivering quality. As identified, the Air Force expects good quality systems and solid security programs to protect classified information against external and internal threats. It is also a goal of this project to perform quality assurance by testing our solution in a Lab environment before delivering it to our client.

- As mentioned earlier, the current security solution used by the Air Force to protect their systems is called HBSS. It turns out that HBSS works in very similar ways to Carbon Black, therefore a challenge raised for Unisys to demonstrate why Carbon Black is a better security solution than HBSS. During communications with the Air Force, the Carbon Black vendors and the Unisys team went over the feature of Carbon Black and how these features can be leveraged to implement a stronger security product than HBSS, however, Unisys still needs to prove to the Air Force that this is actually the case through live demonstrations. Furthermore, there is the likelihood that this demonstration never took place before making a decision about Carbon Black. Let it be known this may or may not have happened while I still wasn’t part of the team.

- The Project Manager could have prevented this by preparing a live demonstration of the new product. Proving that the new product will deliver the quality as established in the contract before moving into the implementation phase. During planning the PM should have set a task apart to prioritize live demonstrations of all the new products before implementing them into production. Doing so would guarantee that the quality that was promised will actually be delivered.

## Knowledge Area 6: Project Human Resources Management

- During the initial phase of the project, Unisys planned to add bodies as required, which is one of the reasons why I was brought on to the team. As tasks become more demanding the need for professionals may increase, which is what happened now that it became clear that none of the current team members have the skills necessary to train Air Force users on the new systems and security solutions. This approach could even speed up the project towards completion or delay it.

- Three months into the project, the Project Manager realized that we didn’t have a training specialist that could train the Air Force personnel on the new systems and security solutions. It wasn’t until before the implementation phase that we decided that a temporary contractor was to be added to the team to take care of the training tasks. The contractor is to create, write and develop training material for our team that we can use to train the Air Force later on. We decided as a team that everyone in the team currently has their plate full working on other tasks, therefore, the contractor position needs to be filled prior to the solution’s deployment (ASAP). The addition of a new member to the team will increase the cost of the project, as he will be receiving hourly pay until his work is completed. IT trainers under a contract usually make anywhere from make about $20h - $40h his contract will be signed for 3 months. The temporary participation of the contractor in the project adds from $9600 - $19200 to the current total project cost.

- The project manager should have developed a chart of all the personnel required at the beginning, middle, and end of the project and adjusted the cost within budget. Doing so would make sure that everyone was on the same page as far as our responsibilities. This would have also made the need for another addition to the team clear during the planning phase

## Knowledge Area 7: Project Communications Management

- This Area somewhat ties into the time management aspect of the project. As mentioned in that section, communication with shareholders is critical to the project’s success. No one can communicate their needs better than the client themselves as well as explain their expectations. When communicating with the client not only does the project become clearer, but also we guarantee that the quality of the services surpasses the client’s expectations.

- Because of lack of communication during the planning phase, a 1 GB/s switch was purchased unnecessarily. The project manager failed to communicate with the Nutanix vendors enough about how the Nutanix solution works from a networking standpoint. Also, because of miscommunications between other vendors and Unisys management there was more money than required to allocate the service of the new systems. Out of only 50 systems that will be replaced, 70 licenses were ordered per product unknowingly. Some money could have been set aside if only the required number of licenses was purchased.

- The project manager could have avoided the drawbacks mentioned above by creating, collecting, storing, and retrieving the necessary information about every aspect of the project. Applying effective communication methods and discussing with other team members should definitely deter the risk of such mistakes occurring again.

## Knowledge Area 8: Project Risk Management

- When carrying out a project, it is critical that risk be managed because failure to do so can bring devastating consequences to a project. The team and I have engaged in several meetings about risk management in which we plan ahead of time and come up with ways of mitigating potential risks. However, not all risk can be mitigated. In such cases it is best practiced to find alternatives to either deal with the risk or reduce it to an acceptable level.

- During one of our meetings, we realized that even though we had come up with a good security solution for the Air Force, we had not yet thought of a way of backing up the data that the applications will produce. Because of this, there is a risk that data may be lost during and outage or disaster. If the Nutanix box breaks, for instance, there would be no way of backing up the data inside it which would be a very high security and operational risk. With the servers being down, the endpoints will not be protected against threats, and become an easy target to malicious insiders or outsiders. This risk must be mitigated last minute because no one had thought about it during the planning phase.

- To prevent issues like this from happening again, it is important to engage in ongoing risk assessments during the entire project. Every progress made in the project can present us with new risks, therefore, uncertainties should be treated carefully at all times. Responding to a risk on time can help keep the project on track and unaffected by the unexpected.

## Knowledge Area 9: Project Procurement Management

- The security solutions, operating systems, and servers (excluding the ones that had already been there) will all be provided by third party vendors. Nutanix, Carbon Black, Bromium, SteelCloud, and Microsoft are the third party vendors that will be involved in this project. Without the vendors’ support the project would fail as we depend on the vendors to plan, select, and monitor the solutions. Establishing relationships with the vendors ensures that the software and solutions ordered are received on time and that they meet the project’s long term goal. The vendors can also demo their solutions and provide assistance during the creation of training for the Air Force and even our own team members.

- Unisys has established a solid relationship with all the vendors, therefore, the solutions will likely to be successful. The Project Manager has made sure to communicate to the vendor the needs of the Air Force so that the vendors can modify their solutions to exceed the Air Force needs.

## Knowledge Area 10: Project Stakeholder Management

- Stakeholders are a critical piece in every organization’s operation. It is important that the right people are selected to participate and are aware of what is going on at the place the hold stakes from. A stakeholders can be anyone from within the organization (in this case the Air Force) as well as anyone who owns a portion of the organization’s assets ((stocks, bonds, etc.). ) and people who hold and interest in a project undertaken by the organization. Aligning the project’s goal with the shareholder’s needs helps drive the project to success as shareholders have a say  and can make partial decisions on the organization’s decisions.

- Since the beginning of the project we failed to include many stakeholders in our weekly and daily discussions. People that needed to participate in the decision making aspect of the project were never invited to meetings as we were never aware that they needed to be participants.

- The project manager could have mitigated this issue by developing a list of shareholders and people of interest and communicating with these people about the project’s goals. Creating the list would have guaranteed a higher attendance rate on all the critical meetings as well as provided us with a lot more insight than we received.

References:

U.S. AIR FORCE. (n.d.). Retrieved November 2, 2019, from https://eastcoastflag.com/collections/military-flags/products/u-s-air-forc

Matrix Organization. (n.d.). Retrieved November 2, 2019, from http://www.kautilyasociety.com/tvph/impact_oriented/matrix_organization_and_matrix_m.htm.