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“Activity Symbol Tmmediate predecessors | Time estimate (weeks)
Investigate demand A 3
Develop pricing strategy B 1
Design product € 5
Conduct promotional cost D A 1
analysis

Manufacture prototype E C 6
models

Perform product cost analysis F E 1
Perform final pricing analysis G BDF 2
Conduct market test H G 8





